## Slide 1
LO5 - Be able to plan to prevent problems with a business event
OCR Level 02 – Cambridge Technical
Unit 07 – Support the Organisation of a Business Event
2016 Specification - J/617/0728

## Slide 2: Assessment Criteria
The Learner will | Pass The assessment criteria are the Pass requirements for this unit. | Merit To achieve a Merit the evidence must show that, in addition to the Pass criteria, the candidate is able to: | Distinction To achieve a Distinction the evidence must show that, in addition to the Pass and Merit criteria, the candidate is able to:
1. Be able to identify resources needed to support the organisation of a business event | P1: Identify the resources they need to source to aid the organisation of an event and any relevant constraints |  | 
2. Be able to source event resources | P2: Investigate sources that can provide the resources required for an event | M1: Identify a range of sources for their resource, including the advantages and disadvantages of each source | D1: Create a best-practice process for others for future booking/arranging of resources, including recommendations for the prevention of issues, based on a review of own experience
3. Be able to make and confirm event arrangements with relevant parties | P3: Arrange for production of, or book, the required resources with their chosen source |  | 
 | P4: Communicate the arrangements for an event to relevant parties, using appropriate communication channels |  | 
4. Be able to inform other team members of progress against the plan | P5: Create a progress report and share it with the event organisation team using appropriate communication channels | M2: Update their report showing dependencies between own tasks and those of others | 
5. Be able to plan to prevent problems with a business event | P6: Take steps to mitigate the likelihood of problems occurring |  | D2: Assess the most likely problems and produce a contingency plan to address them
6. Review your own performance when organising a business event | P7: Review own performance in supporting the organisation of an event, identifying strengths and areas for development | M3: Share and discuss own self-assessment with a colleague to seek their opinions and confirm areas for improvement | 

## Slide 3
To achieve P6, learners should demonstrate that they have planned for their aspect of the event and, in that planning, have taken steps to mitigate the likelihood of problems occurring (e.g. if arranging travel, that they have considered planned rail track maintenance and recommended that the event takes place on a day when maintenance is not planned). They should consider solutions that could avoid or mitigate the negative impact of these potential issues on the event planning.
M2 requires learners to show that they can update their report following team update/s, to take account of the dependencies between their own task and that/those of others (e.g. timeframes for completion may change if a colleague’s task has slipped behind schedule).
D2 requires learners to assess the most likely problems that may occur as a result of their own and the team’s progress, and produce a contingency plan to address the problems. The contingency plan may change over time as issues become apparent with the event organisation.
Assessment Criterion P6, M2, D2

## Slide 4: Assignment Scenario
Supporting an event
Most organisations need to run an event from time to time and so supporting the organisation of an event is an undertaking that most people working within a business administration role will encounter.
Your school/college operates a number of events throughout the year. The Senior Leadership Team (SLT) is aware that you have been studying Business Events as part of your Cambridge Technical course and has asked you to demonstrate what you have learnt throughout your study of this qualification by working as part of a team to support the organisation of an event at your school/college.
The event must be agreed in advance with your tutor and SLT to ensure that it meets the requirements of this unit. Possible events may include:
  Christmas concert ● Outdoor summer music event
  Drama production ● Careers fair
  Regional schools network event ● Science fair
  Host an event for local feeder primary school pupils as part of their ‘moving up’ preparation
  Sports day ● End of year art show
  Curriculum enterprise day for another year group
You will need to work as part of a team, so responsibilities and tasks must be divided as equally as possible. You will be responsible for a specific aspect of the event organisation and the work that you produce will illustrate your individual role.
The team will need to identify and source the resources required to run the event. You will support the production of the event materials and communicate effectively with all relevant parties. During your event preparations you will need to keep the other members of your team informed of your progress and support solutions to any problems that may be encountered to ensure that the event is a success. During the event you will support its running by taking a hands-on role. It is recommended that you keep a diary.
After the event you will review your own performance so you can identify strengths and areas for improvement.

## Slide 5: P6 – Organisation Event Resources
5.1 Understand how to prevent problems occurring i.e.
distribute pre-event documentation/instructions well in advance/according to the plan timescale
conduct rehearsals/dummy runs and pre-checking that resources work effectively
thorough planning (e.g. detailed timescale)
produce well-written schedule of activities
ensure contracts outline roles and responsibilities in detail
contingency planning (i.e. identify possible problems and solutions)
communicating with others
consider the skills of individuals when allocating tasks
ask for support/help promptly
communicate/escalate issues promptly to managers and colleagues (e.g. requests for additional resources)
organise/conduct risk assessments
identify and rehearse venue emergency procedures
5.2 How to deal with problems that could occur
when planning a business event i.e.
last minute requests for resources (e.g. additional photocopying)
technical problems (e.g. technology breakdowns)
team member disagreements
misunderstandings/wrong assumptions/poor communication
issues arising that demand the rearrangement or revision of plans (e.g. venue change)
cancellations (e.g. delegates, speaker, trainer, suppliers, venue, catering)
inadequate room or facilities (e.g. room temperature, seating capacity, lack of technical resources, lighting)
suppliers fail to deliver or deliver wrong items
external factors (e.g. weather and travel disruption)
last minute over or under demand for event by delegates/customers
missing time deadlines
not meeting budget targets
sourcing the wrong resources
not supporting other team members

## Slide 6: P6.1 – Preventative Measures
Very rarely does a project run smoothly, difficulties are found booking, people let you down, deliveries do not arrive on time etc. For P6.1 You have to demonstrate that you understand how to prevent problems occurring i.e. In report first discuss the following problem solutions in relation to your project, and state how you may have met each of these in your project plan or in the event planning itself.
Distribute pre-event documentation/instructions well in advance/according to the plan timescale – There is nothing like leaving it to the last minute, except not doing it. Pre-ordering in advance is the best way to reduce down delivery delays, but only for goods that can be stored securely and do not go off.
Conduct rehearsals/dummy runs and pre-checking that resources work effectively – practicing with the microphones for sound, time the presentations, give some leeway to delays, make sure the trainers are prepared beforehand, reduces issues on the day.
Thorough planning (e.g. detailed timescale) – Following the Gantt chart, preparing each stage in the plan, setting deadlines and controlling the risk. Good event managers excel at this stage, and pre-prepare for problems even if they do not occur.
Produce well-written schedule of activities – Make sure everyone knows what they are doing and when, set timings and compartmentalize duties and tasks so they are easily achieved in small bites.
Ensure contracts outline roles and responsibilities in detail – make sure all the guest speakers and those working for the project from the outside, know exactly what they are supposed to be doing, where and when. This will reduce down the risk of a half done job or extra tasks being performed which slow down the bigger jobs.

## Slide 7: P6.1 – Preventative Measures
Contingency planning (i.e. identify possible problems and solutions) – Drawing into the Gantt chart all possible things that could go wrong with each task and providing a possible reassure for their solution. For instance staff problems attending the Prom, plan for contingency staff or possible parental cover.
Communicating with others – Always keep the lines of communication open, have regular meetings where issues can be discussed and planned for, additional support given to etc. As long as it does not set problems with their tasks.
Consider the skills of individuals when allocating tasks – When choosing your team to perform each phase of the event, choose the best person suited for the job rather than those that want to do it, you are the team leader and the better judge of their skills.
Ask for support/help promptly – When a problem arises, solve it as fast as possible to avoid cascading. Reach deadlines or set more staff to help reach the deadline. And ask for help, from teachers, parents, suppliers.
Communicate/escalate issues promptly to managers and colleagues (e.g. requests for additional resources) – through meetings, bring up resources, who needs more to reach their goals and allocate these resources quickly, better to spend a little more than to double the price when the problem grows.
Organise/conduct risk assessments – Most companies produce a risk assessment for possible issues and rank these in terms of risk levels, this allows preventative measures to be in place. For example, first aid kids at the Martletts, find out beforehand on possible student allergies and plan for it.
Identify and rehearse venue emergency procedures – fire evacuation run-throughs are useful, allocate fire officers from the team, practice procedures.
P6.1 - Task 01 – Discuss possible risks that might occur in your event and explain how these risks might be countered.

## Slide 8: P6.2 – Dealing with Risks
Planning for risks is good but knowing and preparing how to deal with the risks that could not be avoided is the mark of a good events manager. For 6.2, discuss each of the potential problems in context of your event and how for your event you might mitigate these problems. How to deal with problems that could occur when planning a business event i.e.
Last minute requests for resources (e.g. additional photocopying) – there is always someone who has not got enough of something, for instance photocopies or packs for hand outs. For mine, this might be a podium, a projector, additional parking, security.
Technical problems (e.g. technology breakdowns) – This could be laptops, power, projector bulb, speakers, microphone.
Team member disagreements – There will always be some form of conflict, and sometimes this can affect team members, over quality, deadlines, issues with job allocations, taking days off.
Misunderstandings/wrong assumptions/poor communication – sometimes messages get lost in transit, leading to time wasting, delays, disagreements, blaming.
Issues arising that demand the rearrangement or revision of plans (e.g. venue change) – This can be something as small as delivery of bunting for the day, or something as large as hall closure or change of prices of the hall booking.
Cancellations (e.g. delegates, speaker, trainer, suppliers, venue, catering) – This cannot be easily predicted but needs to be considered, especially as the deadline closes. If for instance the DJ cancels, then another one needs to be found, equipment arranged, playlists, meetings, payments and payment recovery etc.

## Slide 9: P6.2 – Dealing with Risks
Inadequate room or facilities (e.g. room temperature, seating capacity, lack of technical resources, lighting) – Even with preparation, there might not be enough of something on the day, or the room is not big enough for the additional guests, or capacity numbers is too much for fire safety.
Suppliers fail to deliver or deliver wrong items – This can happen easily, getting things in advance of the day is good but sometimes bunting with spelling mistakes, balloons with no helium, the wrong drinks order etc.
External factors (e.g. weather and travel disruption) – Cannot be predicted until the day but precautions can be made, people making their own way there dissipates the issues and poor weather cannot be controlled, so ticket purchase in advance is useful.
Last minute over or under demand for event by delegates/customers – this can impact room capacity, seating, tables, food numbers. It is the project managers task to limit this as much as possible before the issue cascades.
Missing time deadlines – Jobs can fail or fall behind, this can impact on follow on jobs (dependencies) , budgets need to be set aside to reduce these risks.
Not meeting budget targets – Money overruns are quite common, a strict control over prices and the budget is necessary, or contingencies made to reduce later purchases in order to pay for the most important ones.
Sourcing the wrong resources – can be reduced but not necessarily avoided, your team is fallible.
Not supporting other team members – conflict resolution and reallocating tasks to help the team move forward. Meetings and team discussions can help plan for this.
P6.2 - Task 02 – Discuss how to deal with potential issues that might occur in your event and explain how these risks might be countered.

## Slide 10: M2.2 – Dealing with Risks
For M2.2 you need to update your report showing dependencies between own tasks and those of others. Discuss how your own tasks as a member of the team will have tasks that depend on the completion of other tem players tasks. Describe the following in your report:
  Name and demonstrate the tasks that depend on others
  Nature of your tasks are that depend on others, with examples.
  Issues with this interdependence.
  Potential impact on the project success if your dependencies do not work out.
  How your team might overcome these issues.
  The impact slippage of your tasks will have on others.
  Who to talk to and how to communicate these issues.
M2.2 – Task 03 – Using example, update your report to discuss the dependencies you have on your role within the project, and others have that could impact your tasks.

## Slide 11: D2.1 – Contingency Planning
For D2.1 you need to assess the most likely problems that might occur during your phase of the project. You need to produce a contingency plan to address them. Take examples from the Gantt Chart you produced and change the chart to show the re-allocation of following tasks following an issue.
Then use the template attached, fill in three likely problems and fill in the contingency plan table.
These three issues need to be considerable. In your report on this show the Gantt chart changes and the table and explain in detail the –reallocation of resources that could be sued to alleviate the risk of these events.
D2.1 – Task 04 – Using the template, Assess the most likely problems and produce a contingency plan to address them.

## Slide 12: LO5 – Assessment Criteria
P6.1 - Task 01 – Discuss possible risks that might occur in your event and explain how these risks might be countered.
P6.2 - Task 02 – Discuss how to deal with potential issues that might occur in your event and explain how these risks might be countered.
M2.2 – Task 03 – Using example, update your report to discuss the dependencies you have on your role within the project, and others have that could impact your tasks.
D2.1 – Task 04 – Using the template, Assess the most likely problems and produce a contingency plan to address them.