## Slide 1
LO4 - Be Able to Prepare Project Plans
Cambridge TECHNICALS- LEVEL 3
Unit 16 – Principles of Project Management
2016 Specification - M/507/8163

## Slide 2: Calculating the Points
e
The number of points available for each unit depends on the unit grade achieved. Units 1 and 22 in the Cambridge Technicals in Business are 120 GLH; all other units are 60 GLH. The table below shows the number of points issued for each grade.
To calculate the learner’s qualification grade you will need to add up all the points for the units the learner has achieved, making sure they’ve covered the appropriate mandatory content, taken sufficient externally assessed units, and any units required for the chosen pathway.
Unit GLH | Points table for units based on GLH |  |  | 
 | Pass | Merit | Distinction | Unclassified
60 | 14 | 16 | 18 | 0
120 | 28 | 32 | 36 | 0

## Slide 3: Qualification Grade Table - Diploma
e
Having calculated the total number of points based on the unit grades you would check this figure in the qualification grade table, for the relevant qualification, to identify the overall qualification grade. If a learner doesn’t achieve the lowest points score required for the qualification, we issue an unclassified result.
Example A
Learner A has taken the units required for the Foundation Diploma:
In this example, Learner A has an overall qualification grade of a Merit Merit.
Unit | GLH | Grade | Number of Points
1 | 120 | Pass | = 28 points
2 | 60 | Merit | = 16 points
3 | 60 | Pass | = 14 points
4 | 60 | Merit | = 16 points
11 | 60 | Distinction | = 18 points
16 | 60 | Pass | = 14 points
17 | 60 | Distinction | = 18 points
20 | 60 | Pass | = 14 points
Total GLH | 540 | Total no. of points | = 138 points

## Slide 4: Qualification Grade Table – Foundation Diploma
e
Qualification grade table OCR Level 3 Cambridge Technical Foundation Diploma (540 GLH)
The table below shows the points ranges and the grades that those ranges achieve.
Points range | Grade | 
156 and above | Distinction* Distinction* | D*D*
153 – 155 | Distinction* Distinction | D*D
150 – 152 | Distinction Distinction | DD
144 – 149 | Distinction Merit | DM
138 – 143 | Merit Merit | MM
132 – 137 | Merit Pass | MP
126 – 131 | Pass Pass | PP
Below 126 | Unclassified | U

## Slide 5: Qualification Grade Table – Technical Diploma
e
Qualification grade table OCR Level 3 Cambridge Technical Diploma (720 GLH)
The table below shows the points ranges and the grades that those ranges achieve.
Points range | Grade | 
208 and above | Distinction* Distinction* | D*D*
204 - 207 | Distinction* Distinction | D*D
200 – 203 | Distinction Distinction | DD
192 – 199 | Distinction Merit | DM
184 – 191 | Merit Merit | MM
176 – 183 | Merit Pass | MP
168 - 175 | Pass Pass | PP
Below 168 | Unclassified | U

## Slide 6: Unit 15 – Learning Outcome (LO) Weightings
Assessment Guidance
All Learning Outcomes are assessed through an externally set written examination paper, worth a maximum of 60 marks and 1 hour 30 minutes in duration.
The assessment comprises short answer questions and questions requiring more extended responses, some will be based on in tray exercises testing skills and underpinning knowledge.
It is important for learners to have the opportunity to learn and apply the knowledge and skills in order to successfully achieve the unit.
Synoptic Learning And Assessment
Ten per cent of the marks in the examination for this unit will be allocated to synoptic application of knowledge. There’ll be questions that draw on knowledge and understanding from Unit 1 The business environment that then has to be applied in the context of this unit.
It will be possible for learners to make connections between other units over and above the unit containing the key tasks for synoptic assessment, please see section 6 of the centre handbook for more detail.

## Slide 7: Assessment Criteria
LO | Pass | Merit | Distinction
1. Understand the stages of project management | P1*: Explain the stages of project management used in a specific business project |  | 
2. Understand the skills project managers need to have | P2*: Explain the skillset a project manager needs to have and why |  | 
3. Understand how and why projects are monitored and factors that influence a project | P3*: Explain how the factors that influence or present a risk to a specific project are monitored | M1: Analyse the factors that influence, and the factors that present a risk to, a specific project and explain the potential impact(s) on the project | D1: Evaluate the effectiveness of the methods used for monitoring a specific project
4. Be able to prepare project plans | P4*: Prepare a project plan for a specific project | M2: Explain how the risks to a specific project could be mitigated. | D2: Evaluate the impact on a specific project if contingencies have to be implemented.
 | P5: Justify the choice of the project plan tool(s) used. |  | 

## Slide 8: 16 – Principles of Project Management – Unit Aim
UNIT AIM
Businesses undertake projects of all kinds that vary in terms of purpose and scope. Some examples of business projects are running an event, launching a marketing campaign, carrying out market research and setting up book keeping for local clubs or charities. A project comprises a set of tasks and activities to be carried out in order to reach an intended purpose. Being able to prepare and manage a project is an important skill needed by many different people working in business.
In this unit you will learn about the stages of project management, and the type of skills a project manager should have. You will also learn why you need to monitor the progress of projects as it is vital to their successful completion and implementation.
You will plan a project, and prepare a project plan. You will learn about the different planning tools available for project planning. Whilst preparing the project plan, you need to be aware of internal and external factors which might have an impact on the planning process, as well as the successful completion and implementation of a project.
This unit will help you to develop the skills required to plan projects and be aware of possible obstacles that can impact on the outcome of a project.

## Slide 9: P4.1 - The Components of a Project Plan
For P4 you need to fill in the Project Plan for your project using the set criteria. This has to be accurate to a degree but not completely. You may need to research a project plan look to see some figures and details and you can use the tasks completes in LO1 to aid you in this section.
Project vision - A Project Vision Statement is an idealistic view of the desired outcomes to be produced for the business after successful project completion. It is a vivid description of what the business will be like to inspire the project beneficiaries to initiate the project. In this you will need to include:
Description of project – What the project is, what needs to be done and why there is a purpose for this project to be completed.
  Key outcomes – What you hope to achieve from the project, how you expect the end result to look and what other people how it will look like and achieve.
  Deliverables – What are the key things that need to be achieved in the project to make it a success, in terms of a product or service that is given to your client. What is it expected to do for them in their business or life.
  Priorities – What are the key list of things to get done, what needs to be focused on, what things need to be done first and be done well for everything else to happen.
Target audience -
  Project stakeholders and their needs – Who are they, what do they want, what are their objectives, what minimum and maximum will need to be done to achieve their goals.
Setting aims and SMART objectives – Draw up a list of aims fore the Project and then draw a set a SMART target for your project and explain each target in detail to be clear on the focus.

## Slide 10: P4.1 - The Components of a Project Plan
Resource requirements – Explain a list of the resources needed, take this from previous tasks and streamline it. These resources need to include a list with explanation of:
Physical resources – All (or some) key resources that you can think of for the project. Be realistic, but no need to be too accurate in amount.
  Materials – Bricks, wood etc. draw up an expected list or research from a prior product what was used to match your own. Be specific on the materials but not on the size or number.
  Equipment – IT equipment, hire equipment.
  Machinery – Whatever machines are required to resource the project. E.g. if you were making a building for woodwork in a school, then band saws, cutters, drills etc.
  Tools – Like machinery, draw up a list of expected tools required and explain the need for these in the plan.
  Software – PM software, and software needed for the finished project, see task 5.2.
Human resources – Who is going to be working on the project and their roles and responsibilities including:
  Project management team – Name and list the responsibilities of the team, names can be made up but remember the examiner does not have a sense of humour. Specify job tasks and skills if necessary to show forethought in this section.
  Support staff – Like above, secretaries, security etc., for the project.
  Key roles and responsibilities – List their duties and responsibilities within the project, there may be duplicates and overlaps but this is fine.
  Own role – Specify your role as Project Manager in this project, responsibilities and name tour role for each section of the project planning including monitoring, evaluation, risk management and quality assurance.

## Slide 11: P4.1 - The Components of a Project Plan
Project schedule – A time plan of what should happen and when, including milestones and dependencies. It needs to be realistic for the project, and include activities such as:
Activities/tasks to be carried out – From the setting up of the team to the Project closure and evaluation, these should be assigned to people with a set value of time, dependencies and relevance.
Who is to complete activities/tasks – The staffing of the tasks with their job titles so that other staff know who to ask and associate with duties.
Timeframes for completion of activities/tasks and utilisation of resources
  Dependencies – what tasks rely on other tasks to be completed. E.g. choice of course or exam board chosen before the books are bought.
  Milestones – What are the key activities in the project to show progress, something that must have a cut off point before progressing.
  Duration – How long each task should take along with contingency timings.
Budget and costings – How much everything should cost including salaries of staff for the project. If you are assuming they are already staff with other jobs then put £0 for their value, otherwise guess.
  Breakdown of salaries – How much staff will be paid for the duration of the project, a monthly breakdown would be better than an overall figure. Ask the teacher for help on salary expectations.
  Consultancy fees – How much outside help will cost in terms of hiring agencies, solicitors, inspectors etc. for the project. If any.
  Materials – Costings for the build, books, room, set up etc. If unsure, ask the teacher, a guessed value will do.
  Venues – How much the rooming will cost and any additional rooms needed for the project.
  Equipment – IT and other things to equip for the build or to equip afterwards.

## Slide 12: P4.1 - The Components of a Project Plan
Contingency plan – What measures you have in place in case of overruns, be specific about the tasks for the project and those that might expect an overrun, specify how long and how much to expect in costings for these.
  Allow time and budget for project risks and issues – Setting a time and cost value for each contingency, should amount to 10% of the value set. E.g. purchase of books for a new course should arrive on time, but expect a 3-7 day delay due to order size and shortages. Extra cost will be £0.
Methods and frequency for communicating project progress to stakeholders – Specify from LO3 tasks how you will talk to the stakeholders, how regular the meetings, be specific about which tasks will need discussing or meeting about. There should be at least three named activities to be sure. Talk about how you will go about this, email, meeting, phone etc. and why this method would be best.
Methods for monitoring - Specify from LO3 tasks how you will monitor the project, rephrase the task to be more clear about the methods, times and what success criteria you are setting.

## Slide 13: P4.1 - The Components of a Project Plan
Methods for evaluation - Specify from LO3 tasks how you will evaluate the project, rephrase the task to be more clear about the methods, times and what success criteria you are setting. Phrase it as:
How to obtain feedback from project stakeholders – Which medium should you take to contact the stakeholders in the close-out document, when should you do this and reasons why chosen.
  Surveys, observation, case studies, focus groups, interviews - Medium used and reasons why.
When to obtain feedback from project stakeholders – When to contact the stakeholders, interim or close-out and why you wait until then.
  Lessons learned on completion of stages of project – Give a summary of the expectations of the completed project, what will your company have gained from doing the project.
How project outcomes meet project vision -
  Benefits received from project outcomes – What expectation have you of the finished version against the initial vision of the project, what can the client expect from the change and how should their vision be managed post production to meet the needs of the change.
  P4.1 – Task 01 – Using the template, prepare a project plan for a specific project.
  For M2, explain in your report at the end on how the problems and risks can be dealt with. You need to draw up a risk assessment plan with an explanation of how you would solve these problems, and these solutions need to be explained in terms of budgets, timings and staffing. You should have at least 5 risks set and 5 contingencies for these risks explained.
  M2.1 – Task 02 - Explain how the risks to a specific project could be mitigated.
  D2.1 – Task 03 - Evaluate the impact on a specific project if contingencies have to be implemented.
  For D2 follow on from M2 and explain in the report at the end the possible consequences of not following the risk assessment and solutions and the issues that will happen when contingencies are put in place. There should be at least 5 circumstances explained well, using titles such as Time, Dependencies, Budgets, Milestones, Staffing and Quality to help explain the consequences of not following the contingency plans.

## Slide 14: P5.1 - Project Management Tools - Purpose
Project management tools are aids to assist an individual or team to effectively organise work and manage projects and tasks. The term usually refers to project management software you can purchase. These tools are not just for project managers and are made to be completely customisable so they can fit the needs of teams of different sizes and with different goals.
Features
Project management tools are usually defined by the different features offered. They include, but are not limited to:
Planning/scheduling – Project management tools allow you to plan and delegate work all in one place with tasks, subtasks, folders, templates, workflows, and calendars.
Collaboration – Email is no longer the only form of communication. Use project management tools to assign tasks, add comments, organize dashboards, and for proofing & approvals.
Documentation – Avoid missing files with file management features: editing, versioning, & storage of all files.
Evaluation – Track and assess productivity and growth through resource management & reporting
Click Here

## Slide 15: P5.1 - Project Management Tools – CPA Diagrams
Critical path analysis (CPA) - This is a widely-used project management tool that uses network analysis to help project managers to handle complex and time-sensitive operations.
Many larger businesses get involved in projects that are complex and involve significant investment and risk. As the complexity and risk increases it becomes even more necessary to identify the relationships between the activities involved and to work out the most efficient way of completing the project.
The essential technique for using CPA is to construct a model of the project that includes the following:
A list of all activities required to complete the project
The time (duration) that each activity will take to completion
The dependencies between the activities
Using this information, CPA calculates:
The longest path of planned activities to the end of the project. The earliest and latest that each activity can start and finish without making the project longer This process determines which activities are "critical" (i.e., on the longest path) and which have "total float" (i.e. can be delayed without making the project longer).
In project management, a critical path is:
The sequence of project activities which add up to the longest overall duration
The critical path determines the shortest time possible to complete the project.
Any delay of an activity on the critical path directly impacts the planned project completion date (i.e. there is no float on the critical path).

## Slide 16: P5.1 - Project Management Tools – CPA Diagrams
Illustration of CPA
Here is worked example to illustrate how the critical path for a project is determined. The main components of a network analysis are summarised below:
P5.1 – Task 04 – Create a CPA diagram of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
M2.2 – Task 05 - Explain how the risks to a specific project could be mitigated with the use of a CPA diagram.

## Slide 17: P5.1 - Project Management Tools – Gantt Chart
Gantt charts - A Gantt chart is a popular project management bar chart that tracks tasks across time. They have become common to track both time and interdependencies between tasks, which is now its everyday use.
Gantt charts have become an industry standard. They are an important project management tool used for showing the phases, tasks, milestones and resources needed as part of a project.
To complete a project successfully, you must control a large number of activities, and ensure that they're completed on schedule. If you miss a deadline or finish a task out of sequence, there could be knock-on effects on the rest of the project. It could deliver late as a result, and cost a lot more. That's why it's helpful to be able to see everything that needs to be done, and know, at a glance, when each activity needs to be completed.
Gantt charts convey this information visually. They outline all of the tasks involved in a project, and their order, shown against a timescale. This gives you an instant overview of a project, its associated tasks, and when these need to be finished.
P5.1 – Task 06 – Create a Gantt Chart of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
M2.3 – Task 07 - Explain how the risks to a specific project could be mitigated with the use of a Gantt charts.
Click Here

## Slide 18: P5.1 - Project Management Tools – PERT
  Program Evaluation and Review Technique (PERT) - The PERT is a model for project management developed as a method for analysing the tasks involved in completing a given project, especially the time needed to complete each task and identifying the minimum time required to complete the total project.
  Both PERT and CPA display the total project with all scheduled tasks shown in sequence and show which ones are in parallel or be performed at the same time. A graph called a CPM Diagram is used to show graphically the relationships of the elements of a project and to show the order in which the activities must be performed. PERT planning involves the following steps:
  Identify the specific activities and milestones. The activities are the tasks of the project. The milestones are the events that mark the beginning and end of one or more activities.
  Determine the proper sequence of activities. Other tasks may require some analysis to determine the exact order in which they should be performed.
  Construct a network diagram. Using the activity sequence information, a network diagram can be drawn showing the sequence of the successive and parallel activities. Arrowed lines represent the activities and circles represent milestones.
  Estimate the time required for each activity. A distinguishing feature of PERT is it's ability to deal with uncertainty in activity completion times. For each activity, the model usually includes three time estimates:
    Optimistic time - the shortest time in which the activity can be completed.
    Most likely time - the completion time having the highest probability.
    Pessimistic time - the longest time that an activity may take.
  From this, the expected time for each activity can be calculated using the following weighted average:
  Expected Time = (Optimistic + 4 x Most Likely + Pessimistic) / 6
  This helps to bias time estimates away from the unrealistically short timescales normally assumed.
  P5.1 – Task 08 – Create a PERT diagram of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
  M2.3 – Task 09 - Explain how the risks to a specific project could be mitigated with the use of a PERT diagrams.

## Slide 19: P5.2 - Project Management Tools – Software Packages
  Software packages - PM software provides businesses, who undoubtedly juggle a number of tasks, with a solution that helps keep them organised. There are a wide variety of PM software packages available, including web-based applications. Each software boasts its own set of features, but they all share common benefits businesses can appreciate.
  Collaborate on Projects - Employees are often assigned individual tasks that are a part of a larger project an entire team is working to complete. Project management software gives employees a way to collaborate on projects by sharing documents, timelines and status updates.
  Delegate Tasks – The Project Manager will likely weigh the knowledge, skills and abilities of employees before delegating tasks to them. Using PM software easily delegates tasks to the appropriate employees. By assigning roles in the system, each employee has access to necessary information and knows who they should contact if they have questions or concerns, or need information about a particular topic.
  Stay on Schedule - PM software lets project managers add a start and expected completion date to projects and tasks they include in the system. This information alerts employees to upcoming deadlines, allowing them to manage their time appropriately to complete tasks before or on the due date.
  Track Projects – They keep track of the progress of projects. The software will let the Manager know what's been completed, as well as by whom, and what still needs to be done. Employees can provide updates as to what they're working on and share their updates with the project manager and team members. The software eliminates the need for status update meetings and emails.
  Communicate with Clients and Vendors - PM software enables businesses to share and collaborate with clients and vendors in addition to employees. Companies using PM software can provide their clients with usernames and passwords giving them access to project files.

## Slide 20: P5.2 - Project Management Tools – Flow Diagrams
  Flow diagrams to plan - Flow Diagrams act as a blueprint -- providing a broad scope of the project. they helps to translate written strategies and mathematical equations into a format that any employee can understand.
  Flow Diagrams Illustrates Project's Overview
  A workflow diagram can act as a project's overview, illustrating the project in a format easily readable to every team member. It helps ensure that all involved parties are on the same page, illustrating the project's timeline, budget and workforce delegation. A department head can use this document to see the impact the project will have on his division and subordinates. Thus, this bird's eye view of the project could help managers to assess its feasibility quicker and provide crucial feedback before the project's initiation
  Flow Diagrams Help Manage Workforce
  A workflow diagram breaks down the team member's functions during each stage of the project, allowing managers to see who is working on what aspect of the project at any given time. The benefit of having this diagram drafted ahead of time is that managers can assess which departments might need to be allocated more human resources to produce the project on time.
  Flow Diagrams Help Avoid Possible Risks
  Planning for errors should happen at every stage of the project, and a flow diagram can help illustrate any contingency plans. At crucial, high-risk stages in the workflow, possible problems are flagged and various backup plans are outlined along with possible outcomes. This workflow diagram allows a manager to see possible errors that will change the flow of work.
  P5.2 – Task 10 – Explain with examples how software packages and Flow Diagrams can be useful tools within a project management scenario and justify the use of these tools within your project plan.
  M2.4 – Task 11 - Explain how the risks to a specific project could be mitigated with the use of a software packages and Flow Diagrams.

## Slide 21: P4, P5, M2 & D2 – Assessment Criteria
  P4.1 – Task 01 – Using the template, prepare a project plan for a specific project.
  M2.1 – Task 02 - Explain how the risks to a specific project could be mitigated.
  D2.1 – Task 03 - Evaluate the impact on a specific project if contingencies have to be implemented.
  P5.1 – Task 04 – Create a CPA diagram of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
  M2.2 – Task 05 - Explain how the risks to a specific project could be mitigated with the use of a CPA diagram.
  P5.1 – Task 06 – Create a Gantt Chart of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
  M2.2 – Task 07 - Explain how the risks to a specific project could be mitigated with the use of a Gantt charts.
  P5.1 – Task 08 – Create a PERT diagram of one of your business project activities, explain this tool within a project management scenario and justify the use of this tool within your project plan.
  M2.3 – Task 09 - Explain how the risks to a specific project could be mitigated with the use of a PERT diagrams.
  P5.2 – Task 10 – Explain with examples how software packages and Flow Diagrams can be useful tools within a project management scenario and justify the use of these tools within your project plan.
  M2.4 – Task 11 - Explain how the risks to a specific project could be mitigated with the use of a software packages and Flow Diagrams.