## Sheet1
1. BASIC RISK INFORMATION |  |  |  |  | 2. RISK ASSESSMENT INFORMATION |  |  |  |  | 3. RISK RESPONSE INFORMATION
Risk Number | Risk Description / Risk Event Statement | Responsible | Date Reported day-month-year | Last Update day-month-year | Impact H / M / L | Impact Description | Probability H / M / L | Timeline N/M/F | Status of Response N / P / PE / EE | Completed Actions | Planned Future Actions | Risk Status Open / Closed / Moved to Issue
Provide a unique identifier for risk | A risk event statement states (i) what might happen in the future and (ii) its possible impact on the project. "Weather" is not a risk event statement. "Bad weather may delay the project" is a risk event statement. | Name or title of team member responsible for risk | Enter the date the risk was first reported | Enter the date the risk (not the entire log) was updated | Enter here H (High); M (Medium); or L (Low) according to impact definitions | List the specific impact the risk could have on the project schedule, budget, scope, and quality. Other impacts can also be listed | Enter here H (High) M (Medium) or L (Low) according to probability definitions | Enter here N (Near-term); M (Medium-term); or F (Far-term) according to timeline definitions | Enter here N (No Plan); P (Plan but not enacted); PE (Plan enacted but effectiveness not yet known); EE (Plan enacted and effective) | List, by date, all actions taken to respond to the risk. This does not include assessing the risk | List, by date, what will be done in the future to respond to the risk | State if the risk is open (still might happen and still has to be managed); closed (has passed or has been successfully mitigated); moved to issue (risk has happened)
Example R 1 | Concrete prices may increase, causing the project to go over budget | Materials Acquisitions Manager | 2005-12-01 | 2006-01-12 | M | The cost of the concrete could be as much as 50% more expensive than budgeted for, resulting in an overall cost overrun of 15% on the project | H | M | PE | 10-Jan-2006: Asked concrete supplier to guarantee a price; request denied | 12-Jan-2006: Investigating cost of purchasing materials now and storing them until needed | Open
Example R 2 | Key supplier may lose a pending lawsuit and go out of business, creating the need to find a new supplier, which will cause schedule delays | Project Manager | 2006-12-15 | 2006-01-12 | H | Finding a new supplier, negotiating contract, and getting re-started is estimated to cause a 6-month delay | N/A | N/A | N/A | 12-Jan-2006: Met with supplier to discuss options 15-Jan-2006: Spoke with other suppliers regarding availability 20-Jan-2006: Prepared contingency plan and RFP in case supplier goes bankrupt 25-March-2006: Moved risk to issue process -- supplier lost lawsuit and declared bankruptcy | N/A | Moved to issue
R 1
R 2
R 3
R 4
R 5
R 6
R 7
R 8
R 9
R 10
R 11
R 12
R 13
R 14
R 15
R 16
R 17
R 18
R 19
R 20
R 21
R 22
R 23
R 24
R 25
R 26
R 27
R 28
R 29
R 30
R 31
R 32
R 33
R 34
R 35
R 36
R 37
R 38
R 39
R 40
R 41
R 42
R 43
R 44
R 45
R 46
R 47
R 48
R 49
R 50
R 51
R 52
R 53
R 54
R 55
R 56
R 57
R 58
R 59
R 60
R 61
R 62
R 63
R 64
R 65
R 66
R 67
R 68
R 69
R 70
R 71
R 72
R 73
R 74
R 75
R 76
R 77
R 78
R 79
R 80
R 81
R 82
R 83
R 84
R 85
R 86
R 87
R 88
R 89
R 90
R 91
R 92
R 93
R 94
R 95
R 96
R 97
R 98
R 99
R 100