## Slide 1
LO1 - Understand the Stages of Project Management
Cambridge TECHNICALS- LEVEL 3
Unit 16 – Principles of Project Management
2016 Specification - M/507/8163

## Slide 2: Calculating the Points
e
The number of points available for each unit depends on the unit grade achieved. Units 1 and 22 in the Cambridge Technicals in Business are 120 GLH; all other units are 60 GLH. The table below shows the number of points issued for each grade.
To calculate the learner’s qualification grade you will need to add up all the points for the units the learner has achieved, making sure they’ve covered the appropriate mandatory content, taken sufficient externally assessed units, and any units required for the chosen pathway.
Unit GLH | Points table for units based on GLH |  |  | 
 | Pass | Merit | Distinction | Unclassified
60 | 14 | 16 | 18 | 0
120 | 28 | 32 | 36 | 0

## Slide 3: Qualification Grade Table - Diploma
e
Having calculated the total number of points based on the unit grades you would check this figure in the qualification grade table, for the relevant qualification, to identify the overall qualification grade. If a learner doesn’t achieve the lowest points score required for the qualification, we issue an unclassified result.
Example A
Learner A has taken the units required for the Foundation Diploma:
In this example, Learner A has an overall qualification grade of a Merit Merit.
Unit | GLH | Grade | Number of Points
1 | 120 | Pass | = 28 points
2 | 60 | Merit | = 16 points
3 | 60 | Pass | = 14 points
4 | 60 | Merit | = 16 points
11 | 60 | Distinction | = 18 points
16 | 60 | Pass | = 14 points
17 | 60 | Distinction | = 18 points
20 | 60 | Pass | = 14 points
Total GLH | 540 | Total no. of points | = 138 points

## Slide 4: Qualification Grade Table – Foundation Diploma
e
Qualification grade table OCR Level 3 Cambridge Technical Foundation Diploma (540 GLH)
The table below shows the points ranges and the grades that those ranges achieve.
Points range | Grade | 
156 and above | Distinction* Distinction* | D*D*
153 – 155 | Distinction* Distinction | D*D
150 – 152 | Distinction Distinction | DD
144 – 149 | Distinction Merit | DM
138 – 143 | Merit Merit | MM
132 – 137 | Merit Pass | MP
126 – 131 | Pass Pass | PP
Below 126 | Unclassified | U

## Slide 5: Qualification Grade Table – Technical Diploma
e
Qualification grade table OCR Level 3 Cambridge Technical Diploma (720 GLH)
The table below shows the points ranges and the grades that those ranges achieve.
Points range | Grade | 
208 and above | Distinction* Distinction* | D*D*
204 - 207 | Distinction* Distinction | D*D
200 – 203 | Distinction Distinction | DD
192 – 199 | Distinction Merit | DM
184 – 191 | Merit Merit | MM
176 – 183 | Merit Pass | MP
168 - 175 | Pass Pass | PP
Below 168 | Unclassified | U

## Slide 6: Unit 15 – Learning Outcome (LO) Weightings
Assessment Guidance
All Learning Outcomes are assessed through an externally set written examination paper, worth a maximum of 60 marks and 1 hour 30 minutes in duration.
The assessment comprises short answer questions and questions requiring more extended responses, some will be based on in tray exercises testing skills and underpinning knowledge.
It is important for learners to have the opportunity to learn and apply the knowledge and skills in order to successfully achieve the unit.
Synoptic Learning And Assessment
Ten per cent of the marks in the examination for this unit will be allocated to synoptic application of knowledge. There’ll be questions that draw on knowledge and understanding from Unit 1 The business environment that then has to be applied in the context of this unit.
It will be possible for learners to make connections between other units over and above the unit containing the key tasks for synoptic assessment, please see section 6 of the centre handbook for more detail.

## Slide 7: Assessment Criteria
LO | Pass | Merit | Distinction
1. Understand the stages of project management | P1*: Explain the stages of project management used in a specific business project |  | 
2. Understand the skills project managers need to have | P2*: Explain the skillset a project manager needs to have and why |  | 
3. Understand how and why projects are monitored and factors that influence a project | P3*: Explain how the factors that influence or present a risk to a specific project are monitored | M1: Analyse the factors that influence, and the factors that present a risk to, a specific project and explain the potential impact(s) on the project | D1: Evaluate the effectiveness of the methods used for monitoring a specific project
4. Be able to prepare project plans | P4*: Prepare a project plan for a specific project | M2: Explain how the risks to a specific project could be mitigated | D2: Evaluate the impact on a specific project if contingencies have to be implemented
 | P5: Justify the choice of the project plan tool(s) used |  | 

## Slide 8: 16 – Principles of Project Management – Unit Aim
UNIT AIM
Businesses undertake projects of all kinds that vary in terms of purpose and scope. Some examples of business projects are running an event, launching a marketing campaign, carrying out market research and setting up book keeping for local clubs or charities. A project comprises a set of tasks and activities to be carried out in order to reach an intended purpose. Being able to prepare and manage a project is an important skill needed by many different people working in business.
In this unit you will learn about the stages of project management, and the type of skills a project manager should have. You will also learn why you need to monitor the progress of projects as it is vital to their successful completion and implementation.
You will plan a project, and prepare a project plan. You will learn about the different planning tools available for project planning. Whilst preparing the project plan, you need to be aware of internal and external factors which might have an impact on the planning process, as well as the successful completion and implementation of a project.
This unit will help you to develop the skills required to plan projects and be aware of possible obstacles that can impact on the outcome of a project.

## Slide 9: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
A project is a planned set of interrelated tasks to be executed over a fixed period and within certain cost and other limitations, for example building a house, making a new product, creating the accounts for a school canteen. It is defined as something that has:
Definite beginning, end and outcome of project so that it can be measured, labelled and arranged with aims and objectives.
Types of business project – Projects vary is shape and size depending on what wants what from it. These types dictate the aims and objectives of a project, how it is run and what sis expected from it, they include:
  Management – A system of change within accompany such as restructuring, setting up a system, creating a department, having a task complete like a company report or opening up in a new market for its goods.
  Manufacturing – A system of introducing the making processes of a new product, streamlining the production processes of a current product or merging technologies to improve the manufacture of a product.
  Construction – Building something like a house, school, factory, bridge, something that has a purpose that will lead to a design and finished version of the product.
  Research - Inventing something, finding out through marketing the need for some new product or looking into why something is not the way it should be, either through marketing or product designing.
  IT - Changing a system for a new system, introducing an IT system into the current environment through direct changeover, phased or concurrent processing.
  P1.1 - Task 01 – Define what a Project is and using different project types and examples, outline the aims and objectives of what a project should achieve.

## Slide 10: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
Project Management – This outlines a range of practical understandings and skills that will make their projects both successful and satisfying. It will provide them with common-sense solutions to the project management issues they will face as they plan and implement a project, and the tools, tips, and techniques it contains are intended to help them achieve consistent success using minimum resources.
In the final analysis, the success as a project manager is down to them; it will depend on their ability to make their vision of “what can be” more influential in their own and other people’s thinking and actions than the reality of “what currently is.”
Project Manager - They are organised, passionate and goal-oriented who understand what projects have in common, and their strategic role in how businesses succeed, learn and change.
Project managers are change agents: they make project goals their own and use their skills and expertise to inspire a sense of shared purpose within the project team. They work well under pressure and are comfortable with change and complexity in dynamic environments. They can shift readily between the "big picture" and the small-but-crucial details, knowing when to concentrate on each.
Project managers cultivate the people skills needed to develop trust and communication among all of a project's stakeholders: its sponsors, those who will make use of the project's results, those who command the resources needed, and the project team members.

## Slide 11: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
Project stakeholders - Stakeholders are those with any interest in your project’s outcome. They are typically the members of a project team, project managers, executives, project sponsors, customers, and users. Stakeholders are people who are invested in the project and who will be affected by your project at any point along the way, and their input can directly impact the outcome.
It’s a good idea to practice good stakeholder management and constantly communicate with them in order to collaborate on the project. After all, they have a stake in how it all turns out.
  Client – The person for whom the project is created for who has the biggest say in its outcome and most to gain from its completion.
  Customers/users – Those who will use the finished results of the project such as students when the management change something in a school or customers when a new product is released.
  Project manager – The person responsible for the beginning, middle and end of a project, the one who makes the plans and carries out the process.
  Project team members – Those members of the project that have a role to play in its outcome such as Heads of Department in a School or change managers in a larger business frame.
  Suppliers – Those involved in the making, supplying and success of a project who are responsible for supplying the materials to carry it out.
  Consultants/contractors – Those people hired from the outside to complete sections or take part in a project that are beyond the capability or skills et of the current hired.
  P1.1 - Task 02 – Define what Project Management, Project Managers and Project Stakeholders are, and using a specific project example, outline the aims roles and objectives of each of these.

## Slide 12: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
A project is broken down into stages to make it more manageable. Stage 1 is the Project initiation – this too is broken down into stages.
Define aims and objectives (SMART), purpose, scope, deliverables, establishing key targets and deadlines - At its simplest level, a project is a “one-time” scope of work defined by five parameters - purpose, scope, deliverables, establishing key targets and deadlines. In other words, it is the means by which a particular purpose is delivered using specified resources to achieve a set result within a set period of time.
  Purpose – What is the project aiming to achieve, set using SMART targets to get there such as starting a new taught course at a school.
  Scope – What is it going to take to get it done, the materials, the measured parameters of the project including costings.
  Deliverables – What can be done using the materials made available, what is it known that can be achieved, the lower limits of the project.
  Establishing key targets – What we would like to achieve, the upper limit, the amount that needs to be done and when it should be done for.
  Deadlines – Timings, start, finish and milestones.
For most projects, one of these five parameters is “fixed” (i.e., should not or cannot change), but there is flexibility in at least one of the other four. Where the scope of the product is fixed (bringing a new drug to market, for example), costs have a tendency to rise and deadlines to slip if work is more extensive or complex than was first envisioned. Where the deadline is fixed (as for a tender deadline or a business conference), people either throw more resources at the project to make sure that it is ready on time, or they cull desirable but nonessential features in order to deliver the essential elements of quality within the timeframe available.

## Slide 13: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
Feasibility study - A feasibility study is an analysis of how successfully a project can be completed, accounting for factors that affect it such as economic, technological, legal and scheduling factors. Project managers use feasibility studies to determine potential positive and negative outcomes of a project before investing a considerable amount of time and money into it.
For example, a small school looking to expand its premises might perform a feasibility study to determine if it should follow through, taking into account material and labor costs, how disruptive the project would be to the students, the public opinion of the expansion, and laws that might have an effect on the expansion, the costs and limits of the build, whether the grants will be available and whether demand dictates that it happens..
A feasibility study tests the viability of an idea, a project or even a new business. The goal of a feasibility study is to place emphasis on potential problems that could occur if a project is pursued and determine if, after all significant factors are considered, the project should be pursued. Feasibility studies also allow a business to address where and how it will operate, potential obstacles, competition and the funding needed to get the business up and running.
For the rest of this project you will need to choose a specific project to discuss the tasks in relation to such as building a new school building, setting a new school subject or one of your choice agreed by the teacher.
P1.1 – Task 03 – Describe and explain with examples from your project choice, what a project Initiation is, the importance of defining Aims and Objectives and what a Feasibility Study is and expects to achieve.

## Slide 14: P1.1 – The Stages of Project Management
Project proposal - A project proposal is a detailed description of a series of activities aimed at solving a certain problem. In order to be successful, the document should provide a logical presentation of a research idea. Once the project leader met with the major stakeholders, they build a project proposal. The proposal is a document that basically captures the information they’ve been gathering informally. The project proposal is solely owned by the project sponsor, and it specifically authorises the project manager to utilize resources to execute the project. Further, the proposal outlines such things as the business need the project is expected to fulfill, the high-level requirements, assumptions, and constraints, the schedule milestones, the budget, the stakeholders, etc. As you would expect.
Business case - The business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. All projects must have a business case that demonstrates the value of the work.
In the concept phase of the life cycle an outline business case is prepared that is then used by senior management to assess whether to give the go-ahead for the definition phase. The detailed business case is prepared during the latter phase.
The project is owned by the sponsor, who has ultimate accountability for ensuring that the benefits are achieved. However, the project manager will usually be responsible for preparing the business case, possibly with specialist support. A business case typically includes the:
strategic case – the background of the project or program and why it is needed;
options appraisal – what options have been considered and which has been chosen (not forgetting the ‘do nothing’ option);
expected benefits – the benefits that will arise from the work and any unavoidable negatives;
commercial aspects – the costs, investment appraisal and funding arrangements;
risk – the major risks and their impact on the business case;
timescales – a summary of the delivery of outputs and realisation of benefits.
P1.1 – Task 04 – Using the scenario, discuss what a Project proposal Document and a Business Case are, ownership, objectives and what they hope to achieve.
P1.1 – Task 05 – Using the template here, and the guide here, create, customise and complete a project proposal for your selected scenario.

## Slide 15: P1.1 – The Stages of Project Management
A School project could be for a subject, lesson, series of lessons or to benefit the overall school day. Planning your revision timetable for exams could be considered a project. Not all project plans mean a successful outcome. Every marketing plan is a project that is planned and executed with a purpose and outcome. At some point you will either create a project in life or be part of someone else’s project plan.
Define project controls (e.g. time, cost, quality strategies) - Project controls are the data gathering, management and analytical processes used to predict, understand and constructively influence the time and cost outcomes of a project or program; through the communication of information in formats that assist effective management and decision making. This definition encompasses all stages of a project or program’s lifecycle from the initial estimating needed to ‘size’ a proposed project . This includes:
Project strategy, undertaking planning and methods studies to help the PM optimise future outcomes;
Scheduling including development, updating and maintenance;
Cost estimation, cost engineering/control and value engineering;
Risk management, including maintaining the risk register and risk analysis/assessment;
Document control;
Supplier performance measurement / oversight (but excluding contract administration);
Put simply, Project Controls encompass the people, processes and tools used to plan, manage and mitigate cost and schedule issues and any risk events that may impact a project.

## Slide 16: P1.1 – The Stages of Project Management
Define communication strategy - Given the organisational and geographical diversity of project teams – it is important to consider all methods of communication. Technology allows us to communicate easily where ever the team members may be. A communication strategy should be conceived at the project planning stages, so key is its influence on the success of the project. Communication methods can either be active or passive.
ACTIVE communication methods being those used to communicate in the here and now, for example the use of:
Face to Face meetings
Video conference, meeting – one on one, or group
Telephone conference, or voice only web conference
Webinars, becoming increasingly popular for the delivery of presentation based activities
Telephone – good old fashioned call
Stand up presentations in person
PASSIVE communication methods would be those which recipients can adopt in their own time, for example:
Pod cast or Web cast
Email
Intranet bulletin boards
Blogs
Website
Project newsletter – paper based
Table top presentation
P1.1 – Task 06 – Using the scenario, describe and discuss how Defining project Controls and Define a Communication Strategy benefit a project, including ownership, objectives and what they hope to achieve.
P1.1 – Task 07 – Using the template here, and the guide here, create, customise and complete a communication plan for your selected scenario.

## Slide 17: P1.2 – Project Planning
Project planning – Producing an accurate and detailed plan is one of the project manager’s most important responsibilities. However, do not make the mistake of thinking they should do it on their own. By involving team members in the planning process they increase their understanding of what has to be done and often gain an extra level of commitment to deadlines. This usually consists of five stages:
Project plan - A project plan, according to the Project Management Body of Knowledge (PMBOK), is a formal, approved document used to guide both project execution and project control. The primary uses of the project plan are to document planning assumptions and decisions, facilitate communication among project stakeholders, and document approved scope, cost, and schedule baselines. A project plan may be summarized or detailed.
It can be the contract that the project sponsor and project manager use to agree on the initial vision of the project (scope, baseline, resources, objectives, etc.) at a high level. The project management plan is the most important document for describing a project during the initiation and planning phases.
Resource plan (e.g. what is needed - human resource requirements, tools and equipment – and when) - This Project Resource Management Plan helps a manager to identify all of the resources required to complete the project successfully. Using this Resource Plan, a manager will be able to identify the quantity of labour, equipment and materials needed to deliver the project.
The manager will then create a resource schedule, which enables them to plan the consumption of each type of resource, so that they know that they will have enough resources to complete the project. Contents usually contain:
Types of labour required for the project and Number of people required to fill each role
Roles and key responsibilities for each labor type
Items of equipment to be used and their purposes and types and quantities of equipment needed
Identify the amount of resource required per project activity and the total amount of materials needed
Plan the dates for using or consuming these resources
P1.2 – Task 08 – Using the scenario, discuss how what a project Plan and Resource Plan are, their benefit to a project, including ownership, objectives and what they hope to achieve.
P1.2 – Task 09 – Using the template here, and the guide here, create, customise and complete a Project plan for your selected scenario.

## Slide 18: P1.2 – Project Planning – Financial Planning
Financial plan (e.g. sources of finance - corporate budget, external funding - timescales for release of finances) - If a manager want to deliver projects on time and under budget, then they need a Project Financial Plan to help them do it. A financial plan consists of:
A List of the Financial Expenses The first step taken when defining a Financial Plan and setting a project budget, is to identify all of the types of expenses that are likely to be incurred throughout the Project Lifecycle. These may include:
Procurement of resources from suppliers
Establishment of a Project Office
Administration of the project
Quantify the Financial Expenses Once they have identified a detailed list of expenses to be incurred throughout the project, the next step is to forecast the unit cost of each expense type listed. The unit cost is simply the cost of a single unit of a particular expense item. For instance, the unit cost for:
labor may be calculated as the cost per hour supplied
equipment may be calculated as the rental cost per day
materials may be calculated as the purchase cost per quantity
Construct an Expense Schedule Next, a manager has now collated all the information needed to build a detailed expense schedule. This schedule enables the Project Manager to calculate the total cost of undertaking the project on a daily, weekly or monthly basis.
Define the Financial Process Next, a manager has created the Expense Schedule, they will need to define the process for monitoring and controlling expenses (i.e. costs) throughout the Project Lifecycle. Define the Cost Management Process for your project by documenting the fixed and variable costs of the key resources.
P1.2 – Task 10 – Using the scenario, discuss what a Financial Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.

## Slide 19: P1.2 – Project Planning – Quality Assurance Planning
Quality plan (e.g. to set quality targets and quality control methods) - The Quality Management Plan defines the acceptable level of quality, which is typically defined by the customer, and describes how the project will ensure this level of quality in its deliverables and work processes. Quality management activities ensure that:
Products are built to meet agreed- upon standards and requirements
Work processes are performed efficiently and as documented
Non-conformances found are identified and appropriate corrective action is taken
Quality Management plans apply to project deliverables and project work processes.
Quality control activities monitor and verify that project deliverables meet defined quality standards.
Quality assurance activities monitor and verify that the processes used to manage and create the deliverables are followed and are effective.
Quality Plan Components
The Quality Management Plan describes the following components:
Quality objectives
Key project deliverables and processes to be reviewed for satisfactory quality level
Quality standards
Quality control and assurance activities
Quality roles and responsibilities
Quality tools
Plan for reporting quality control and assurance problems
Purpose
The purpose of developing a quality plan at the Stage 3 level is to elicit the customer’s expectations in terms of quality and prepare a proactive quality management plan to meet those expectations.
The Quality Management Plan helps the project manager determine if deliverables are being produced to an acceptable quality level and if the project processes used to manage and create the deliverables are effective and properly applied.
P1.2 – Task 11 – Using the scenario, discuss what a Quality Assurance Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.

## Slide 20: P1.2 – Project Planning – Risk Management Planning
Risk plan (e.g. identification of risks, severity of risk, risk owner, contingencies, documentation of risks and actions) - Risk management planning is the process of deciding how to approach and plan the risk management activities for a project. The Risk Management Plan determines how risks will be identified, monitored, controlled, and eliminated. It also defines the team roles and responsibilities for risk management.
Risk Identification - Risk is identified as “determining which risks might affect the project and documenting their characteristics.” There are two main types of risks: Organisation and External. Organisational risks include inconsistent cost, time, and scope objectives, lack of funding, or resource conflicts with other projects. External risks may involve legal or labor issues. These include:
Historical information from previous projects
Documentation reviews of prior project files
Gathering information by brainstorming, interviewing, or SWOT analysis
Risk log of all possible risks
Assumptions analysis to explore the risk’s validity
Diagramming techniques, such as cause/effect diagrams or a system flow chart
Risk Response Planning - There are four main ways that people respond to risk.
Avoidance – change the project plan to eliminate the risk. By choosing not to do part of the project, you may be scaling down the project’s return on investment.
Transference – shift the consequence and management responsibility of a risk to another party. You can do this by purchase insurance or hiring an expert to do the work.
Mitigation – take early action to reduce the chances of a risk occurring or at least reduce the impact the risk will have on the project when it does occur.
Acceptance – make no changes in the project plan to deal with a risk. Active acceptance monitors the risk and develops a contingency plan in case a risk does occur. Passive acceptance, on the other hand, has you waiting to deal with risks as they occur.
P1.2 – Task 12 – Using the scenario, discuss what a Risk Management Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.
You will need to explain identification of risks, severity of risk, risk owner, contingencies, documentation of risks and actions.

## Slide 21: P1.3 – Project Direction
Project direction (executing and implementing) – Once all the planning is done, it is time to go ahead with the project, stick to time tables, deliverables, minimise risks and manage communications throughout the project to make sure it is on track and on budget.
Manage project controls (e.g. time, cost, quality, risk) - Control comprises tracking performance against agreed plans and taking the corrective action required to meet defined objectives. All four fundamental components of delivery need to be controlled:
  Time – Trying to stay on track, failure to do so means overruns and tasks that rely on others to be complete will fall behind in starting, cascading through the project.
  Cost – Cost overruns and budget compromises mean that a project may not get complete due to degrading standards or costs spiraling.
  Quality – monitoring this during the project cycle means maintaining a standard expected or risking the objective of the project.
  Risk – managing these during the project means minimising disruption. Failure to manage these risks can cause delays, prosecution and reputation.
Report project status - Reporting the project status as a part of the project documentation allows a project manager to monitor the project’s progress. The progress is quantified in the reports, so instead of flying blindly and hoping for the best, the manager have a solid foundation that will help them make more informed decisions. It also enables the project manager to justify why they made changes to the project plan.
Status reports also guarantee that the manager has a constant information flow. It allows them to manage and communicate with their stakeholders more effectively. Stakeholders are always anxious to know how the project is doing, so keeping them in the loop via regular status reports will increase their confidence in the project manager and the project.

## Slide 22: P1.3 – Project Direction
Manage communications - As the project manager, they are the hub of all communication within the project team and between the project team and the outside world. At different stages of the project they will find yourself dealing with different stakeholders, but the three constant lines of communication they need to maintain are with the sponsor, the client, and the team.
Engaging your sponsor and client
Communication with the sponsor should be seen as a high level of openness and trust from the start of the project. They need to spend time establishing how the communication will work, discuss scheduled communication and agree on when and how to expect ad-hoc communication to take place. Give warning of any decisions that need to be made and present facts to the sponsor in a written form for consideration including any action points.
Communication with the client will tend to be more formal than with the sponsor. As with the sponsor, it is important to give the client notice of any decisions. The client relationship can occasionally contain an element of politics, particularly if the client is under pressure from members of his or her business.
Talking to your team
It is always good to maintain an open and honest relationship with the team. In large teams, there is always a danger of some people being left out of the loop when decisions are made or new information becomes available. Make sure you have accurate distribution lists set up for email and documents. On larger and longer running projects, you may find it helpful to post general information on an intranet site to which team members have access.

## Slide 23: P1.3 – Project Direction
Manage risk - Initial identification of risk during the running of the project often takes the form of a Risk Workshop—a group of people getting together with the express purpose of identifying and evaluating all the risks in a particular project or phase.
From that point on every review meeting should contain an agenda item on “open” or “live” risks. As a project manager, the risks you should be most concerned with are those that will have an impact on one of the three project parameters (time, cost, or quality).
Risks need to be evaluated with respect to two criteria: probability (how likely they are to happen) and impact (how serious it would be if they do). Most tasks in your project will contain some element of risk, so you will need to set a threshold at which you are going to begin to plan.
Managing these during the project limits damage, reduces slowdown, reduces costs, especially if something serious might happen.
P1.3 – Task 13 – Using the scenario, explain and discuss in terms of Project Direction what to Manage Project Controls, Reporting Project Status, Managing Communications and Managing Risk are, why they are important and how they can be used to direct a successful project running process.

## Slide 24: P1.4 – Project Closure and Post Implementation Review
Project closure and post implementation review - The Project Closure Phase is the fourth and last phase in the project life cycle. In this phase, you will formally close your project and then report its overall level of success to your sponsor. Project Closure involves handing over the deliverables to your customer, passing the documentation to the business, cancelling supplier contracts, releasing staff and equipment, and informing stakeholders of the closure of the project.
After the project has been closed, a Post Implementation Review is completed to determine the projects success and identify the lessons learned.
Review of project - Projects are different to business as usual because they have an end point at which they can be declared complete and then have their success evaluated.
Even if you are the only person working on a project, it is still helpful to mark the “go live” point. This will send a clear signal that the project is finished and that you and the rest of the project team will be moving on. The four things that should be verified in the review include:
  Extent to which aims and objectives have been met – For a project to be successful, it needs to meet most if not all of the aims and objectives set for the project. E.g., if the project was a building then you would expect it be complete, walls, doors, windows, electricity, plaster etc. and all working.
  Business benefits delivered – To complete the project is not enough, it also has to be of some benefit to the company, saving time, money, leading to better things. Without this then it should not have been started.
  Customer requirements met – Is it good enough in terms of quality, build, price, safety etc., for the customer. Have they agreed on the final standards and verified the requirements.
  Whether remained within time and budget – Has the project been done in time and for the right money, too much and it loses its purpose for some projects and if not done in time then the customer or client will be out of pocket.

## Slide 25: P1.4 – Project Closure and Post Implementation Review
Identify lessons learned – Businesses define lessons learned as the learning gained from the process of performing the project. Formally conducted lessons learned sessions are traditionally held during project close-out, near the completion of the project. However, lessons learned may be identified and documented at any point during the project's life cycle. The purpose of documenting lessons learned is to share and use knowledge derived from experience to:
Promote the recurrence of desirable outcomes
Preclude the recurrence of undesirable outcomes
As a practice, lessons learned includes the processes necessary for identification, documentation, validation, and dissemination of lessons learned. Utilisation and incorporation of those processes includes identification of applicable lessons learned, documentation of lessons learned, archiving lessons learned, distribution to appropriate personnel, identification of actions that will be taken as a result of the lesson learned, and follow-up to ensure that appropriate actions were taken.
  Strengths – What went well with the project in terms of meeting deadlines, staff enrichment, deliverables, costings, timings, meeting the clients needs or meeting the needs of the customers in terms of the finished product.
  Weaknesses – What did not go well, times etc. also who were the weak staff during the process, which staff should be excluded form a similar project, what staff gained from their part, did they perform well.
  Areas for improvement – based on the scenario and all the elements involved, what could be done better next time, what follow on things could be followed in order to make the project more beneficial in its completed state.
  It is important to know these not just to make the project better but to prepare for future projects, to improve staffing, to be better at the accuracy of project planning in the future.
  P1.4 – Task 14 – Using the scenario, explain and discuss in terms of Project Direction what a Review of the Project is, why identifying Lessons learned is important and why this stage of the project management process is important to the future of the company or similar projects..

## Slide 26: P1 – Assessment Criteria
P1.1 - Task 01 – Define what a Project is and using different project types and examples, outline the aims and objectives of what a project should achieve.
P1.1 - Task 02 – Define what Project Management, Project Managers and Project Stakeholders are, and using a specific project example, outline the aims roles and objectives of each of these.
P1.1 – Task 03 – Describe and explain with examples from your project choice, what a project Initiation is, the importance of defining Aims and Objectives and what a Feasibility Study is and expects to achieve.
P1.1 – Task 04 – Using the scenario, discuss what a Project proposal Document and a Business Case are, ownership, objectives and what they hope to achieve.
P1.1 – Task 05 – Using the template here, and the guide here, create, customise and complete a project proposal for your selected scenario.
P1.1 – Task 06 – Using the scenario, describe and discuss how Defining project Controls and Define a Communication Strategy benefit a project, including ownership, objectives and what they hope to achieve.
P1.1 – Task 07 – Using the template here, and the guide here, create, customise and complete a communication plan for your selected scenario.
P1.2 – Task 08 – Using the scenario, discuss how what a project Plan and Resource Plan are, their benefit to a project, including ownership, objectives and what they hope to achieve.
P1.2 – Task 09 – Using the template here, and the guide here, create, customise and complete a Project plan for your selected scenario.
  P1.2 – Task 10 – Using the scenario, discuss what a Financial Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.
  P1.2 – Task 11 – Using the scenario, discuss what a Quality Assurance Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.
  P1.2 – Task 10 – Using the scenario, discuss what a Risk Management Plan is, the benefit to a project, including ownership, objectives and what they hope to achieve.
  P1.3 – Task 11 – Using the scenario, explain and discuss in terms of Project Direction what to Manage Project Controls, Reporting Project Status, Managing Communications and Managing Risk are, why they are important and how they can be used to direct a successful project running process.
  P1.4 – Task 12 – Using the scenario, explain and discuss in terms of Project Direction what a Review of the Project is, why identifying Lessons learned is important and why this stage of the project management process is important to the future of the company or similar projects.