## Slide 1: Unit 09
Project Planning with IT
Y/601/7321
LO1 - Understand how projects are managed

## Slide 2: LO1 - Assessment Criteria
Learning Outcome (LO) The learner will: |  | Pass The assessment criteria are the pass requirements for this unit. The learner can: |  | Merit For merit the evidence must show that, in addition to the pass criteria, the learner is able to: | Distinction For distinction the evidence must show that, in addition to the pass and merit criteria, the learner is able to:
1 | Understand how projects are managed | P1 | Illustrate typical phases of a project life cycle |  | 
 |  | P2 | Explain the resources available to support the project manager | M1 Compare different project methodologies | 
 |  | P3 | Discuss issues affecting project management | M2 Explain the impact identified issues would have on a project | 
2 | Be able to plan projects using IT | P4 | Produce a project specification |  | D1 Evaluate how different delivery mediums for graphics influence file formats
 |  | P5 | Plan a defined project using IT | M3 Create a PERT chart for your defined project | D1 Evaluate the use of Gantt and PERT Charts in project planning
3 | Be able to follow project plans | P6 | Follow a project plan to carry out a defined project | M1 Use advanced editing tools to enhance images | 
4 | Be able to review the project management process | P7 | Carry out a review of the project management process |  | D2 Recommend improvements for future projects using the findings from the project review

## Slide 3: Assessment Criteria P1, P2 and M2
Assessment Criterion P1 - The learner is required to show an understanding of a project lifecycle and illustrate the typical phases. They must describe each of the following phases; analysis, design, implementation and evaluation. The learners could also provide any supporting images/diagrams.
Assessment Criteria P2 - The learner is required to describe and explain the resources available in order to support a project manager throughout a project including data, roles and responsibilities of people involved with the project, funding, equipment and project management software.
Assessment Criteria M1 - The learner should provide a detailed comparison of project methodologies. At least three different project methods should be fully described and compared providing advantages and disadvantages for each of them. This could be presented as a report or annotated table.
Assessment Criteria P3 - The learner must discuss the issues which can affect a project to include; lack of management leadership, communication, external factors changing, conflicts between staff and/or clients, unrealistic timescales, poor testing, quality of product, tracking progress, following legislation.
Assessment Criteria M2 - This should include a description of how these issues would impact the project’s success or failure including some examples of projects that have failed and some reasons for their failure. This could be an extension of P3 or a separate document.

## Slide 4: LO1 - Understand how projects are managed
Learners should be introduced to the concept of the project life cycle and what is involved in the various stages. This could be group working through a project discussing the phases and researching each phase in smaller groups to identify what is carried out at each stage and why. This could be discussed as a larger group and applied to different projects and the outcomes and details compared and approaches discussed.
Learners should be made aware of a range of resources that they may use within different projects and discuss the resources and types to understand what the scope of the term resource covers. They could discuss the resources as a group in relation to the projects previously reviewed and identify the resources that they think would require for that project. Learners should be encouraged to research the roles and responsibilities of the various positions involved in a project e.g. project managers, product developers, programmers and system analysts to identify their use as resources and the implications within the project. This could be done in small groups where each group is provided with one job role and then they could give feedback to the main group.
Learners should also review the hardware and software requirements for a given project, considering the data to be maintained, the reporting etc. A demonstration on how to create a Gantt chart using the relevant software should be given by the tutor, learners should then be encouraged to create a brief Gantt chart using the previous project as a basis. An activity on how to use the critical path method to create a PERT Chart could be carried out either individually or as a group. Different project methodologies could be given to learners working in pairs and they could be encouraged to identify benefits and drawbacks for their project method. They could then give feedback to the group.
Learners should be encouraged to identify issues which may affect a project, they can use information from other projects they have reviewed as a starting point for group working. For each issue that they identify they should be encouraged to find a solution for it. Case studies of big projects that have failed to meet targets e.g. late delivery of project, over budget could be used for the learners to identify what the problems were, how they affected the project and what could have been done differently. A wider group discussion of issues will ensure wider coverage and awareness for learners.

## Slide 5: Project Management Cycle

## Slide 6: P1.1 – Life Cycle – Analysis Phase – Defining the Goal
The first stage of organising and managing an event is defining the goal with the client and venue organiser, clarifying the need for a project scope. The goal can be large or small but needs definition, goals, a point at which it can be defined as started or finished, e.g. maybe your boss thinks of a new market to explore; or maybe you think of a way to refine your organization’s procurement process.
Sometimes the initiating process is informal. For a small project, it may consist of just a discussion and a verbal agreement. In other instances, especially for larger projects, a project requires a formal review and decision by your boss and/or other members of your organisation’s senior management team.
Scope – Defining the value for which a project has a success or failure
Information - The need for Accuracy, timely, and complete data for the planning, performance monitoring, and final assessment of the project
Communication: Clear, open, and timely sharing of information with appropriate individuals and groups throughout the project’s duration
Commitment: Team members’ personal promises to produce the agreed-upon results on time and within budget

## Slide 7: P1.1 – Life Cycle – Analysis Phase – Defining the Goal
For small projects, this entire life cycle can take a few days. For larger projects, it can take many years! In fact, to allow for greater focus on key aspects and to make it easier to monitor and control the work, project managers often subdivide larger projects into separate phases, each of which is treated as a mini project and passes through these four life cycle stages. No matter how simple or complex the project is, however, these four stages are the same.
In a perfect world, you complete one stage of your project before you move on to the next one; and after you complete a stage, you never return to it again. But the world isn’t perfect, and project success often requires a flexible approach that responds to real situations that you may face, such as the following:
You may have to work on two (or more) project stages at the same time to meet tight deadlines. Working on the next stage before you complete the current one increases the risk that you may have to redo tasks, which may cause you to miss deadlines and spend more resources than you originally planned. If you choose this strategy, be sure people understand the potential risks and costs associated with it
Sometimes you learn by doing. Despite doing your best to assess feasibility and develop detailed plans, you may realize you can’t achieve what you thought you could. When this situation happens, you need to return to the earlier project stages and rethink them in light of the new information you’ve acquired.
Sometimes things change unexpectedly. Your initial feasibility and benefits assessments are sound and your plan is detailed and realistic. However, certain key project team members leave the organization without warning during the project. Or a new technology emerges, and it’s more appropriate to use than the one in your original plans. Because ignoring these occurrences may seriously jeopardize your project’s success, you need to return to the earlier project stages and rethink them in light of these new realities.

## Slide 8
All projects undertaken are done so for a reason, because the company needs training, an event that needs organising, external help being called for a purpose etc. Television programmes such as Hotel Inspector are created around this basis, something needs to be done and done properly therefore the demand is created. With each justification comes criterion that needs to be met in order for it to be successful and these are based on the business needs of the client:
  How and why your project came to be
  the business need(s) it addresses
  the scope of work to be performed
  how it will affect and be affected by other related activities
Be sure to distinguish between drivers and supporters as you seek to find your project’s initiator
  Drivers have some say when defining the results of the project. They tell you what you should do.
  Supporters help you perform your project. They tell you what you can do.
For example, the vice president of finance who requests a project to upgrade the organization’s financial information systems is a project driver. The manager of the computer centre who must provide staff and resources to upgrade the organization’s information systems is a project supporter.
P1.1 – Task 1 – Explain the importance of defining the Goal and the Analysing the Problem for a project in order to meet the success criterion.
P1.1 – Life Cycle – Analysis Phase – Problem Analysis
Defining the goal | Problem Analysis

## Slide 9
Project management is the process of guiding a project from its beginning through its performance to its closure. Project management includes five sets of processes, all of which rely on resources being in place. No point starting until you are sure you can complete it: The best projects are those that know their limitations, those where the processes are ensured before the project begins.
Initiating processes: Clarifying the business need and the state of the current system, defining high-level expectations and resource budgets, and beginning to identify audiences that may play a role in your project
Planning system processes: Detailing the project scope, time frames, resources, and risks, as well as intended approaches to project communications, quality, and management of external purchases of goods and services
Executing processes: Establishing and managing the resources available for the current system, communicating with and managing system audiences, and implementing the project plans
Monitoring and controlling system processes: Tracking performance and taking actions necessary to help ensure project plans are successfully implemented and the desired results are achieved
Closing processes: Ending all project activity to meet the project aims and current systems ability.
P1.2 – Life Cycle – Analysis Phase – System Investigation

## Slide 10: P1.2 – Life Cycle – Analysis Phase – Feasibility Study
A feasibility study is an analysis of the viability of an idea. The feasibility study focuses on helping answer the essential question of “should we proceed with the proposed project idea?” All activities of the study are directed toward helping answer this question.
Feasibility studies can be used in many ways but usually focus on proposed business ventures. Managers and others with a business idea should conduct a feasibility study to determine the viability of their idea before proceeding with the development of a business proposal. Determining early that a business idea will not work saves time, money and heartache later.
A feasible business venture is one where the business will generate adequate cash-flow and profits, withstand the risks it will encounter, remain viable in the long-term and meet the goals of the founders. The venture can be either a start-up business, the purchase of an existing business, an expansion of current business operations or a new enterprise for an existing business.
Feasibility studies usually become part of what is called a Scope Statement which is a written confirmation of the results your project will produce and the terms and conditions under which you’ll perform your work. Both the people who requested the project and the project team should agree to all terms in the Scope Statement before actual project work begins.
P1.2 – Task 2 – Explain the importance of System Investigating and a Feasibility Study for a project in order to meet the success criterion.

## Slide 11: P1.3 – Life Cycle – Analysis Phase – Preparing a Project Proposal
Now the feasibility study, investigating and purpose has been defined, the last stage of getting a project off the ground is the proposal, the state where the contractor bring the proposal to the client for agreement. A proposal needs to clarify to the client the 6 stages of agreement, failing on any of these can cause problems later on in the project and blame if the project is not meeting expectations. It is also something that the success criterion of a project will be measured on:
Justification: How and why your project came to be, the business need(s) it addresses, the scope of work to be performed, and how it will affect and be affected by other related activities
Objectives: The products, services, and/or results your project will produce (also referred to as deliverables)
Product scope description: The features and functions of the products, services, and/or results your project will produce
Product acceptance criteria: The process and criteria for accepting completed products, services, or results
Constraints: Restrictions that limit what you can achieve, how and when you can achieve it, and how much achieving it can cost
Assumptions: Statements about how you will address uncertain information as you conceive, plan, and perform your project
P1.3 – Task 3 - Explain the importance of preparing a convincing Project Proposal for a project in order to meet the success criterion.

## Slide 12: P1.4 – Life Cycle – Design Phase – Producing Possible Solutions
When a Project has been agreed the first stages of solving a problem are arranged. There might be multiple solutions to a problem but only one can take place. Restrictions on budget, time, place, manpower and resources will be determined based on setting an objective, or target.
Make your objectives SMART, as follows:
Specific: Define your objectives clearly, in detail, with no room for misinterpretation.
Measurable: State the measures and performance specifications you’ll use to determine whether you’ve met your objectives.
Achievable: Set challenging objectives that encourage people to stretch beyond their comfort zones.
Realistic: Set objectives the project team believes it can achieve.
Time sensitive: Include the date by which you’ll achieve the objectives.
Make your objectives controllable. Make sure that you and your team believe you can influence the success of each objective. If you don’t believe you can, you may not commit 100 percent to achieving it (and most likely you won’t even try). In that case, it becomes a wish, not an objective.

## Slide 13: P1.4 – Life Cycle – Design Phase – Producing Possible Solutions
Identify all objectives. Time and resources are always scarce, so if you don’t specify an objective, you won’t (and shouldn’t) work to achieve it.
Be sure the client and team agree on your project’s objectives.
When the client buys into your objectives, you feel confident that achieving the objectives constitutes true project success. When your development team buy into your objectives, you have the greatest chance that people will work their hardest to achieve them. If the client don’t agree with your objectives, revise them until they do agree. After all, your clients’ needs are the whole reason for your project! If your team don’t buy into your objectives, work with them to identify their concerns and develop approaches they think can work.
P1.4 – Task 4 – Explain the importance of setting SMART objectives to produce possible solutions and how these objectives can have an impact on the success of a project.

## Slide 14: P1.5 – Life Cycle – Design Phase – Designing Aspects of the System
As stated, there are many solutions to a project but only one that fits. Once a project starts there will be negotiations on what way to do each stage, where those states intercept, which resources can be replicated, which Pert or Gantt to use. Pre-empting the stages will save on resources and time. This is where the initial stage comes into its own, a meeting of minds when all staff involved state what way they will tackle a task, when and how and what resources will be necessary.
Another term for this is Project Skills Audit – We are all good at something, better at databases than Spread sheets, more capable of solitary working than team work. Drawing up plans in terms of Gantt and Pert needs to take all these into consideration before the stages begin, specifically if tasks rely on the completion of other tasks.
Breaking down each aspect of the system and planning these states allows for a more effective management of a project. Effective project managers spend as much time preparing aspects as stages in order to reach a goal.
P1.5 – Task 5 – Explain the importance of pre-designing Aspects of a system and how a good system plan can have an impact on the success of a project production.

## Slide 15: P1.6 – Life Cycle – Implementation Phase – Creation - Teams
Your project team typically includes people with different skill sets and operating styles who work in different parts of the organization. You may not have worked extensively with these people before. In addition, your project usually has a tight time schedule, and team members most likely are working on several other projects at the same time.
Success in this environment requires that you all agree how to work with each other to maximize contributions and minimize wasted time and mistakes. The team needs an approach that gives everyone confidence that members will live up to their commitments. The team leader and every team member must understand and be comfortable with the planned roles. The following concepts can help you define and clarify how team members should relate to each other and to their assigned tasks:
Authority: The ability to make binding decisions about your project’s products, schedule, resources, and activities. Examples include your ability to sign purchase orders not to exceed £3,000 and your ability to change a scheduled date by no more than two weeks.
Responsibility: The commitment to achieve specific results. An example is your promise to have a draft report ready by March 1.
Accountability: Bringing consequences to bear in response to people’s performance. An example: Your boss notes in your annual performance appraisal that you solved a difficult manufacturing problem. Unfortunately, many people think accountability means paying the price when you foul up. This fear often causes people to avoid situations where they’ll be accountable for their performance. Paying a price when you foul up is certainly half of the concept, but the other half is being rewarded for doing a good job. This positive reinforcement is far more effective than negative reinforcement to encourage high-quality results.
P1.6 – Task 6 – Explain the importance of setting specific Team Roles in terms of Authority, Responsibility and Accountability and how this can have an impact on the success of a project.

## Slide 16
Project assignments always have deadlines. So even though you’re not sure what your new project is to accomplish, you want to know when it has to be finished. Unfortunately, when you do find out the end date, your immediate reaction is often “But I don’t have enough time!”
The truth is, when you receive your project assignment, you usually have no idea how long it’ll take. First reactions tend to be based on fear and anxiety more than facts, especially if you’re trying to juggle multiple responsibilities and the project sounds complex.
You need an organized approach to clarify how you plan to perform your project’s activities, what schedules are possible, and how you’ll meet deadlines that initially appear unrealistic. This chapter describes a technique that helps you proactively develop your schedule possibilities.
Event - An event is a significant occurrence in the life of your project, sometimes called a milestone or a deliverable. Events take no time and consume no resources; they occur instantaneously. Think of them as signposts that signify a certain point in your trip to project completion. Events mark the start or finish of one activity or a group of activities. Examples of events are draft report approved and design begun.
P1.7 – Life Cycle – Implementation Phase – Creation - Scheduling

## Slide 17
Activity - An activity is the work to go from one event to the next in your project. Activities take time and consume resources; they describe action. Examples of activities are design report format and identify needs for new product. Make sure you define activities and events clearly. The more clearly you define them, the more accurately you can estimate time and resources, the more easily you can assign the task to someone else, and the more meaningful your tracking becomes.
Span time - Span time is the actual calendar time to complete an activity, also called duration. The amount of work effort, people’s availability, and whether people can work on an activity at the same time all affect the activity’s span time. Capacity of non-personnel resources (for example, a computer’s processing speed and the pages per minute that a copier can print) and availability of those resources also affect span time. Delay can also add to an activity’s span time. If your boss spends one hour reading your memo after it sat in her inbox for four days and seven hours, the activity’s span time is five days, even though she spent only one hour reading it. Understanding the basis of a span-time estimate helps you to figure out ways to reduce it.
P1.7 – Task 7 – Explain the importance of setting specific Scheduling Targets in terms of Event, Activity and Span Time and how this can have an impact on the success of a project.
P1.7 – Life Cycle – Implementation Phase – Creation - Scheduling

## Slide 18
Figure 1 illustrates a resources matrix for non-personnel resources. The matrix displays the following information for every lowest-level activity in your project
Work Breakdown Structure
The non-personnel resources to perform the activity
The required amount of each resource
Figure 2 illustrates a computer usage chart for your task. The chart indicates that Task 1 requires ten hours of computer time in Weeks 1, 2, and 3, respectively.
The final requirement for a successful project is sufficient funds to secure the necessary people and resources. All major project decisions (including whether to undertake it, whether to continue it, and — after it’s done — to determine how successful it was) must consider the project’s costs.
In addition to personnel, your project may require a variety of other resources (such as furniture, fixtures, equipment, raw materials, and information) that are important to your project’s success. Plan for these non-personnel resources the same way you plan to meet your personnel requirements.
P1.8 – Life Cycle – Implementation Phase – Creation - Funding

## Slide 19
Figure 3 summarises the weekly usage of all resources for the project.
All project resources cost money. In a world of limited funds, you’re constantly deciding how to get the most return for your investment. Therefore, estimating a project’s costs is important for several reasons:
It enables you to weigh anticipated benefits against anticipated costs to see whether the project makes sense.
It allows you to see whether the necessary funds are available to support the project.
It serves as a guideline to help ensure that you have sufficient funds to complete the project.
Although you may not develop and monitor detailed budgets for all your projects, knowing how to work with project costs can make you a better project
manager and increase your chances of project success.
P1.8 – Task 8 – With the use of specific tables, explain the importance of setting specific Finding Targets and how this can have an impact on the success of a project.
P1.8 – Life Cycle – Implementation Phase – Creation - Funding

## Slide 20
All good projects have documentation produced at the end in order to benefit the client in the uses of the materials. This might be something as simple as an explanation of what was done or something as complicated as a manual that explains each part of the project. Think of a computer game production (Unit 15 or 10), website (Unit 12), database (Unit 23) or spreadsheet (Unit 19), the user will need to know how to use it, where the menus go, what links to what how to purchase, what the FAQ’s and Troubleshooting expectations are.
Production of user documentation should be as prepared as the project, the user will need to be on this product day after day, they will refer to the manual as often as necessary to get used to the completed project specifics. In some ways this is like testing, it needs to be concise, address every issue and anticipate problems.
P1.9 – Task 9 – Explain the importance of organising User Documentation and the need for precision and quality in terms of addressing user issues.
P1.9 – Life Cycle – Implementation Phase – Creation – User Documentation

## Slide 21
Testing - Throughout the creation of a project a good production manager will test that the project is on track and the completed tasks are satisfactory. Similarly when a project is complete and before launching the company will test every feature for problems and potential problems.
There is nothing worse for a company than a user recall and nothing more unprofessional that badly designed and buggy products. Testing should clarify this, web testing of every page, soak testing of a produced game, validation and testing of structure and integrity of a database, precision and formula testing of a spreadsheet.
Maintenance - Maintenance is what happens when testing was not good enough, errors show up, problems are found, bug releases, recalls. Maintenance can lead to improvements, leading to happier customers. Maintenance is the fixing of these found errors. Service pack 1 and 2 of Windows XP fixed the issues with the OS years after release, interim patches fixed them in the meantime. Companies do this as a service, it becomes an expectation of the client.
P1.10 – Task 10 – Explain the importance of Testing and Maintenance, discuss different methods available and explain with examples how these can have an impact on the success of a project.
P1.10 – Life Cycle – Implementation Phase – Creation – Testing and Maintenance
Testing | Maintenance

## Slide 22
Training – The bigger the project the more there will be a need to train staff in how to use, manage, construct or develop a product. Sales staff will be trained to use or sell it, support staff will be trained to manage problems, Users will be trained on how to effectively use the product and those who train others will be trained to a higher level. When you walk into an Apple store you should expect the staff to know more about the products and their uses than you, this is the same with any project, those who deliver should support others within the company.
Launching – Now the product is complete, the launching of the product is something that needs careful planning. Do it too soon and the product might still have bugs, do it too late and the product could have a rival that was not there before. Do it at a price too high and reduce sales, too low and be seen as cheap. Do it in the wrong season and reduce sales, do it in the wrong area and alienate your customer base. This is the reason why companies spend so much money on Market Research and promotion, similarly this is why companies set so much money aside for marketing. For every film released, 60% of the budget is spent on marketing and promotion, 10% on average for actors, 5% for legal issues, leaving just ¼ of the budget on production. Time the launch wrong and that could all be wasted.
P1.11 – Task 11 – Explain the importance of Training and Launching and how the quality and timing of these can have an impact on the success of a project.
P1.11 – Life Cycle – Implementation Phase – Creation – Testing and Maintenance
Training | Launching

## Slide 23
Feedback from Users – product is released, it is on the market, companies do not just sit back and hope that the sales roll in. Websites for instance (Unit 12) have feedback so that the company can improve the effectiveness of the site, a better site, happier customers. When a project is in house (made by them) then their own users give feedback to improve the effectiveness of the project. This will be linked to maintenance. Secondly feedback from users makes them feel valued, that they are changing things and hence more likely to remain loyal.
Project Review – For the project managers the review at the end of a project is there for one reason only, to make them more effective when planning a similar or other project. This is the EBI of project management. When a project is hugely successful and runs completely to order, there is little that can be learned, mistake are almost always made and learned from, timings, budgets, contractors that should be hired or avoided, locations that are not good, staff that are ineffective or prove themselves. All this is written and gathered by successful project managers. Good project managers adapt, better project managers learn.
P1.12 – Task 12 – Explain the importance of Feedback and Project Reviewing and how assessing the failures and successes of a project can have an impact on the success of a future project.
P1.12 – Life Cycle – Evaluation Phase – Evaluation – Feedback and Review
Feedback from Users | Review of Project

## Slide 24: P2.1 – Resources – Data Usage – Previous and Current
There are three kinds of informational resources a project manager can access to benefit the product of any product, Prior system information, Current Data and Researched information.
Prior Data – Whether it is a project that was similar that was done before or access to previous results benefits a project manager because there is always some thing to learn from the past. If a previous project was completed and reviewed, this information can lead to knowledge of what worked well, what went wring and the mistakes that could be avoided. Think of Apple and the next generation of product, they have all the sales, delivery, production, capacity and feedback from 5 generations of Apple sales to work with. Knowledge of this reduces similar mistakes being made.
Current Data – Things change, production methods improve, previous mistakes may not be made. Working with current data, up to date data, can push a project along, New staff, new skills, new production methods, new Financing sources like crowdsourcing etc. working with tis data and understanding this data can make a project more successful. When new cars are made, they have all the prior history and current technologies in there, a history of improvements.
Researched data – New information, new methods of getting this information can improve the effectiveness of project management. A successful project is one that cuts all the ropes that hold it back, new sources for materials, new markets to open up, new places to work from or work with. A successful project manager should know to use the old and the new, the current and the trending information to further benefit costing, production methods, planning tools and final output.
P2.1 – Task 13 – Explain with examples the importance of using Current, Prior and Researched information for project management and how this can have an impact on the success of a project.

## Slide 25: P2.2 – Resources – Personnel
For all project levels of staffing, Project Managers, Developers and Programmers, it is necessary to estimate the work effort that each person has to invest to successfully carry a project through:
Describe in detail all work to perform the activity. Include work directly and indirectly related to the activity. Examples of work directly related to an activity include writing a report, meeting with clients, performing a laboratory test, and designing a new logo. Examples of indirect work include training to perform activity related work and preparing periodic activity-progress reports.
Consider history. Past history doesn’t guarantee future performance. It does, however, provide a guideline for what’s possible. Determine whether an activity has been done before. If it has, review written records to determine the work effort. If written records weren’t kept, ask people who’ve done the activity before to estimate the work effort they invested. When using prior history to support your estimates, be sure
  The people had qualifications and experience similar to those of the people who’ll work on your project.
  The facilities, equipment, and technology were similar to those that’ll be used for your project.
  The time frame was similar to the one you anticipate for your project activity.

## Slide 26: P2.2 – Resources – Personnel
Have the person who’ll do the work participate in estimating the required work effort. Having people contribute to their work-effort estimates provides several benefits: Their understanding of the activity improves; the estimates are tailored for a person with their particular skills, knowledge, and prior experience; and their commitment to do the work for that level of work effort increases. If you know who’ll be working on the activity, have those people participate during the initial planning. If people don’t join the project team until the start or during the project, have them review and comment on the plans you’ve developed.
Consult with experts familiar with this type of activity, even when they haven’t performed work exactly like it before. Experience and knowledge from all sources improve the accuracy of your estimate.
For all three levels of staffing in this stage, the successful completion of the project needs to take this into consideration when allocation functions. The level of role depends on the project, how well the developers will work with the programmers, how much hands on the Project Manager is at the development stage and where the developers job stops and the programmers job starts.
P2.2 – Task 14 – Explain the importance of organising Personnel in terms of Work Activity, Considered History and Work Effort and how this can have an impact on the success of a project.

## Slide 27
A project budget is a detailed, time-phased estimate of all resource costs for your project. You typically develop a budget in stages — from an initial rough estimate to a detailed estimate to a completed, approved project budget. On occasion, you may even revise your approved budget while your project is in progress.
Direct costs are expenditures for resources solely used for your project. Direct costs include salaries for team members on your project; specific materials, supplies, and equipment for your project; travel to perform work on your project; and subcontracts that provide support exclusively to your project.
Indirect costs are expenditures that may support more than one project but aren’t individually allocated to them. Indirect costs fall into two categories:
  Overhead costs: Expenditures that are difficult to subdivide and allocate directly. Examples include employee benefits, office space rent, general supplies, and the costs of furniture, fixtures, and equipment. You need an office to work on your project activities and office space costs money. However, your organisation has an annual lease for office space, the space has many individual offices and work areas, and people work on numerous projects throughout the year. Because you have no clear record of your office’s rent, your office space is treated as an indirect project cost.
  General and administrative costs: Expenditures that keep your organisation operational (if your organisation doesn’t exist, you can’t perform your project). Examples include salaries of your contracts department, finance department, and top management as well as fees for accounting and legal services.
P2.3 – Resources – Funding Sources and Costing

## Slide 28
Suppose you’re planning to design, develop, and produce a company website, database, spreadsheet, game or multimedia product.
Direct costs for this project may include the following:
  Labour: Salaries for you and other team members for the hours you work on the project
  Materials: The special paper stock, DVD’s, CD Covers, scanners, printers, cameras etc. for the project
  Travel: The costs for driving to investigate firms that may design your project cover
  Subcontract: The services of an outside company to design the cover art
Indirect costs for this project may include the following:
  Employee benefits: Benefits in addition to your salary while you’re working on the project
  Rent: The cost of the office space you use when you’re developing the produced materials for the project
  Equipment: The computer you use to compose the premise for the project
  Management and administrative salaries: A portion of the salaries of upper managers and staff who perform the administrative duties necessary to keep your organisation functioning
  P2.3 – Task 15 – Explain with examples the importance of planning for specific Resources spends in terms of Direct and Indirect costs and how this can have an impact on the success of a project.
P2.3 – Resources – Funding Sources and Costing

## Slide 29: P2.4 – Resources – Equipment and Packages
For every project there will be equipment needs, computers, monitors, desk space, rooms, network storage and backups, printers, scanners etc. All these need to be purchased or set aside for the production of the product. For large productions this can be expensive and time consuming, and a great deal of organising. If it is a company and a small project then time set aside, computer time, staff training etc.
Then there are the package needs, Access, Adobe suite, Office, Game Engines. For every IT project there is a package, these have to be purchased or ensured, be in place, be capable, be reliable and staff will need to know how to use them. For a large company and large project the software might be bespoke, adapted software for the specific use, this is common for high end projects like banks. The software might need to be adapted to make it more suitable for purpose.
P2.4 – Task 16 – Explain with examples the importance of planning for specific Resources spends in terms of Equipment and Software costs and how this can have an impact on the success of a project.

## Slide 30: P2.5 – Resources – PM Software Packages
Project management software has the capacity to help plan, organise, and manage resource pools and develop resource estimates. Depending on the sophistication of the software, it can manage estimation and planning, scheduling, cost control and budget management, resource allocation, collaboration software, communication, decision-making, quality management and documentation or administration systems.
For the project manager to successfully complete a project and manage the stages, keep track of progress and monitor deadlines there are professional packages that are designed beyond Excel to do this. If the project is going to take one day to complete then Excel will do. For all other projects, specifically those with a lot of resources, staff, issues and stages there are others. More common ones include:
Microsoft Project – is designed to assist a project manager in developing a plan, assigning resources to tasks, tracking progress, managing the budget, and analysing workloads.
OpenProj - was an open source project management software application which means free, capable and adapted by users for their own needs.
P2.5 – Task 17 – Explain with examples the importance of Project Management Software and how this can have an impact on the success of a project.

## Slide 31
For this section you will need to choose which project you have completed or will work on as the basis of the merit criteria. For example the planning, creation, development and testing of the Game production (Unit 10), the Website (Unit 12), the Animation (Unit 14), the Multimedia Production (Unit 17), the Spreadsheet (Unit 19), the Database (Unit 23) or the Graphic Production (Unit 27), project plans, purpose and audience, briefs and planning charts will all be relevant and mapped to this unit.
Your first step toward a successful project is to develop a plan to produce the desired results on time and within budget. If your project lasts a relatively short time and you’re thorough and realistic in your planning, then most likely your project will be a success.
However, the larger, more complex, and longer your project is, the more likely some aspects won’t work out as you envisioned. Remember, “The best laid plans . . ..” You have the greatest chance for success if you confront the possibility of changes head-on and if you plan how to minimise the consequences of those changes from the outset.
Your first step toward a successful project is to develop a plan to produce the desired results on time and within budget. If your project lasts a relatively short time and you’re thorough and realistic in your planning, then most likely your project will be a success.
However, the larger, more complex, and longer your project is, the more likely some aspects won’t work out as you envisioned. Remember, “The best laid plans…” You have the greatest chance for success if you confront the possibility of changes head-on and if you plan how to minimise the consequences of those changes from the outset.
P3.1 – Project Issues – Risk Management

## Slide 32: P3.1 – Project Issues – Risk Management
Risk is the possibility that you may not achieve your product, schedule, or resource targets because something unexpected occurs or something planned doesn’t occur. All projects have some degree of risk because predicting the future with certainty is impossible.
  The longer your project lasts.
  The longer the time between preparing your project plan and starting the work.
  The less experience you, your team or company may have with similar projects.
  The newer your project’s technology.
The first step in deciding whether to deal proactively with a risk is assessing the likelihood that it will occur. To negate the risk Project Managers follow similar steps below:
  Assess the Probability of occurrence: You can express the likelihood that a risk will occur as a probability. Probability is a number between 0 and 1, with 0.0 signifying a situation will never happen, and 1.0 signifying it will always occur. (You may also express probability as a percentage, with 100% meaning the situation will always occur.)
  Assess the Category ranking: Classify risks into categories that represent their likelihood such as high, medium, and low, or always, often, sometimes, rarely, and never.
  Assess the Ordinal ranking: Order the risks so the first is the most likely to occur, the second is the next most likely, and so on.
  Assess the Relative likelihood of occurrence: If you have two possible risks, you can project a relationship. For example, you can declare the first as twice as likely to occur.
  P3.1 – Task 18 – Explain the importance of Preparing Risk Analysis information in terms of Risk, Category and Probability and explain how this can have an impact on the success of a project

## Slide 33: P3.2 – Project Issues – Management and Communication
Communication (e.g. between project managers and clients) - When deciding how to communicate with your team and your project’s audiences choosing the right medium is as important as deciding what information to share. This choice ensures that people get the information they need when they need it. Lack of communication can be the cause of disruption, bad decisions or pushing the project off track.
Project communications come in two forms:
  Formal communications are pre-planned, conducted in a standard format in accordance with an established schedule. Examples include weekly team meetings and monthly progress reports.
  Informal communications occur as people think of information they want to share. Informal communications occur continuously in the normal course of business. Examples include brief conversations by the water cooler and e-mails you dash off during a day.
Taking care not to rely on informal interchanges to share important information about your project with the client can cause a lack of interaction, specifically dangerous as the client is the only one who is sure of that the outcome should look like. To minimise the chances for misunderstandings and hurt feelings:
  Confirm in writing any important information that you share in informal discussions.
  Avoid having an informal discussion with only some of the people who are involved in the topic.
Both formal and informal communications can be written or oral.

## Slide 34: P3.2 – Project Issues – Management and Communication
Regularly scheduled team meetings give Stakeholders the opportunity to share progress and issues and to sustain productive and trusting interpersonal relationships. These meetings also provide an opportunity to reaffirm the project’s focus and to keep members abreast of activities within and outside the project that affect their work and the project’s ultimate success. Recognising that most people work on several projects at the same time, these meetings can reinforce the team’s identity and working relationships.
Consult with team members to develop a meeting schedule that’s convenient for as many people as possible. If some people can’t attend in person, try to have them participate in a conference call. Meeting should observe the following guidelines when planning and conducting team meetings:
  Even though the meetings are regularly held, always prepare a specific agenda, distribute it beforehand, and solicit comments and suggestions before the meeting.
  Before the meeting, distribute the progress report for the most recent performance period.
  Distribute beforehand any other background information related to topics on the agenda.
  Limit discussions that require more in-depth consideration; deal with them in other forums.
  Start on time and end on time.
  Prepare and distribute brief minutes of the meeting.

## Slide 35: P3.2 – Project Issues – Management and Communication
Lack of management leadership – Every good project has a leader, every successful department has a leader, school, business, team, take away the leader or choose one who does not drive the project and the project starts to fail. Leadership means decision making, guiding the project forward, discussing the needs with the client, formalising the project etc. See Unit 01, LO1.
When a leader does not do these tasks, deadlines slip, budgets go over, decisions are made on the spot without the consultation of other departments and those involved. Think of a football team where everyone wants to score so they all play in the forward line. Think of any company and there is a head that guides and decides.
P3.2 – Task 19 – Explain with examples the importance of Management Leadership and Communication between client and project manager and how failing on this issue can have an impact on the success of a project.
  M2.1 – Task 20 – Using your chosen project, explain the impact Lack of Leadership and Poor Communication would have on a project.

## Slide 36: P3.3 – Project Issues – External Factors and Conflicts
External factors changing (e.g. finance, staff members etc.) Conflicts between staff and/or clients – this is the unpredictable side of Project Management. Things happen beyond the control of the Project that often cannot be predicted. Some influences are minor, a change of weather, cancelled venues, introduced laws, supplier shortages, staff shortages, the client altering a brief, some can be major, change of leadership, change of focus, change of skills or equipment or financial.
With the Kyoto earthquake the price of processors went up by 10% overnight, they came down again in a month but suddenly there was this change. Companies adapt by changing budgets, cutting back, finding new suppliers.
With the client conflicts often change plans, the bar is raised or lowered, budgets can change, jobs can be cancelled. Similarly with suppliers for a project, situations change all the time, adapting, compensating and moving on is the key to success.
Similarly internal conflicts with staff during a project can cause disruption. On larger projects that take months, this is a long time to work with someone, personalities clash, staff take time away pushing deadlines and often leave leaving a vacancy and work to catch up on.
P3.3 – Task 21 – Explain with examples how external factors including conflict with the client can have an impact on the success of a project.
  M2.2 – Task 22 – Using your chosen project, explain the impact External Factors and Conflicts would have on a project.

## Slide 37: P3.4 – Project Issues – Quality and Testing
Internal factors that can have an impact on the success of a project can be managed with careful planning but not all these can be predicted.
Poor testing – this can lead to bugged results. There are different kinds of testing for any project, for instance a game development goes through Alpha, Beta, Gold and Soak, but even then errors can get through. Glitches happen. Similarly with websites, links do not always work, sites change or move, validation can have problems. Databases can produce erroneous results if not checked, spread sheets can produce faulty results if one formula is wrong anywhere.
Quality of product – Similarly even with testing and improving and fault fixing, the quality of the finished product is not guaranteed. Microsoft make great devices and produced a powerful phone but it was just not good enough against Samsung and Apple. Sometimes all the money and power in the world is just not a good compensation for genius. Similarly with any project, it might suit the clients needs, therefor successful, but not the audiences desires, hence lack of sales.
P3.4 – Task 23 – Explain with examples how Poor testing and Finished Quality of Product can have an impact on the success of a project.
  M2.3 – Task 24 – Using your chosen project, explain the impact Poor testing and Quality of the Finished Product would have on a project.

## Slide 38: P3.5 – Project Issues – Timescales and Tracking
Clients have their goals, how much it should cost when it should be complete, how it should look. Setting unrealistic goals and not verifying project ideals along the line can lead to a project failing.
Unrealistic timescales – Lack of time means cutting corners, leads to faults, budget overruns, lack of clarity of finished work, and stress. Project managers are used to working under pressure but staff are not. A project manager would not take on a job if they did not feel confident about achieving the task on time but as stated before goals change, clients change their plans and this causes timescales to change.
Poor Tracking progress of project – It is the job of every good Project Manager to track the progress of a project. If plans are slipping then they need to speed things up to get back on track, if plans are ahead of schedule then everything that relies on that task needs readjusting so there is no lax of work. Without the constant monitoring, the tracking, the scheduling and adapting, deadlines slip, and this can cost money. Overruns are notorious ion the Film industry and millions can be lost is a month, on projects specifically time based, this can be devastating.
P3.5 – Task 25 – Explain with examples how Unrealistic Timescales and Poor Progress Tracking can have an impact on the success of a project.
  M2.4 – Task 26 – Using your chosen project, explain the impact Unrealistic Timescales and Poor Progress Tracking would have on a project.

## Slide 39: P3.6 – Project Issues – Guidelines and Legislation
Every Project has ramifications when it comes to legality and internal guidelines. Databases projects need to take into consideration the DPA, Website the Computer Misuse Act, Games have the PEGI and Intolerance laws and Spread sheets have the Sales of Goods Act to deal with (overcharging customers). Privacy comes under any system that has names and addresses, anything with images can cause discrimination and copyright infringement. Not taking these into consideration can cause all sorts of issues later on.
Similarly internal guidelines can cause project delays, working hours, race and sex representation, pay guidelines, rights of internal information access etc. Giving someone the right to be on a project does not give them the automatic right to see information used in the project.
Worst case scenario is legal issues, failure to abide by laws such as the Data protection Act or child protection can lead to prosecution
P3.6 – Task 27 – Explain with examples how not following Internal Guidelines and being aware of Legislation can have an impact on the success of a project.
  M2.4 – Task 28 – Using your chosen project, explain the impact Internal Guidelines and Awareness of Legislation would have on a project.

## Slide 40: M1.1 – Project Management – Project Methodologies
Within Project Management there are tools that are used to help managers work towards their final goals, each as useful as the other and each with their own merits.
PRojects IN Controlled Environments (PRINCE2): Originally developed for IT projects, PRINCE2 was released in 1996 as a generic project management methodology by the U.K. Office of Government Commerce (OCG). Click here for details.
It is the de facto standard in the United Kingdom and is used in over 50 countries. PRINCE2 defines 45 separate sub-processes and organises them into eight process groups as follows:
1. Starting up a project
2. Planning
3. Initiating a project
4. Directing a project
5. Controlling a stage
6. Managing product delivery
7. Managing stage boundaries
8. Closing a project

## Slide 41: M1.1 – Project Management – Project Methodologies
The Waterfall Model - The Waterfall method follows a managed project in a very sequential and structured way. Planning along the way is minimised because it is all done up-front and a working system is not produced until the end of the life cycle. The idea of a waterfall is a metaphor for a cascading of activities from one phase to the next. This approach stresses a sequential and logical flow of development activities.
For example, the design activities begin only after the analysis and requirement activities are complete. Subsequently, the actual development, or programming activities, will not start until the design phase is complete. Although users can go back to a previous stage, it is not always easy or desirable to do so as the next phase will have begun.
This approach is suitable when developing structured systems and assumes, or at least hopes, that the requirements defined in the analysis stage do not change very much over the remainder of the project. Also, because it will provide a solid structure that can minimise wasted effort, this method may work well when the project team is inexperienced or less technically competent.
The alternative to this is the Agile Method.

## Slide 42: M1.1 – Project Management – Project Methodologies
The Traditional Approach - A traditional phased approach identifies a sequence of steps to be completed. Typical development phases of a project include:
  Project initiation stage;
  Project planning or design stage;
  Project execution or production stage;
  Project monitoring and controlling systems;
  Project completion stage.
Traditional approaches all for the users to go back through stages, pause stages, refresh or restart stages etc. but there will be consequences, delays, problems if the next tasks are linked to the successes of the previous tasks.
Like any undertaking, projects need to be performed and delivered under certain constraints. Traditionally, these constraints have been listed as "scope," "time," and "cost". Delaying, pausing or restarting any of these can have implications for the next phase.
  Time constraint refers to the amount of time available to complete a project.
  Cost constraint refers to the budgeted amount available for the project.
  Scope constraint refers to what must be done to produce the project's end result.
  The traditional Approach does not guarantee closure but does improve quality, a trade off depending on the nature of the project.

## Slide 43: M1.1 – Project Management – Project Methodologies
Many projects fail to meet schedule expectations. Critical path method (CPM) is a network diagramming technique used to predict total project duration. This PM tool helps a manager combat project schedule overruns. A critical path for a project is the series of activities that determine the earliest time by which the project can be completed. It is the longest path through the network diagram and has the least amount of slack or float.
Slack or float is the amount of time an activity may be delayed without delaying a succeeding activity or the project finish date.
Normally, several tasks are done in parallel on projects, and most projects have multiple paths through a network diagram. The longest path or the path that contains the critical tasks is what drives the completion date for the project. You are not finished with the project until you have finished all the tasks.
Even though the critical path is the longest path, it represents the shortest time required to complete a project. If one or more activities on the critical path take longer than planned, the whole project schedule will slip unless the project manager takes corrective action.

## Slide 44: M1.1 – Project Management – Project Methodologies
Project teams can be creative in managing the critical path. For example, Joan Knutson, a well-known author and speaker in the project management field, often describes how a gorilla helped Apple Inc. complete a project on time. Team members worked in an area with cubicles, and whoever was in charge of the current task on the critical path had a stuffed gorilla on top of his or her cubicle. Everyone knew that person was under the most time pressure and did not need distractions. When a critical task was completed, the person in charge of the next critical task received the gorilla.
Alternatively the client may wish to use their own methodologies, mixing others, reducing the amount of stages, adding levels, of subcontracting the development stage.
M1.1 - Task 29 – Produce a report that describes and compares three Project Management Methodologies that are used within Business Planning.
M1.2 – Task 30 – Research and describe the range of advantages and disadvantages of these methodologies.

## Slide 45: Assessment Task List – Part 3
P1.1 – Task 1 – Explain the importance of defining the Goal and the Analysing the Problem for a project in order to meet the success criterion.
P1.2 – Task 2 – Explain the importance of System Investigating and a Feasibility Study for a project in order to meet the success criterion.
P1.3 – Task 3 – Explain the importance of preparing a convincing Project Proposal for a project in order to meet the success criterion.
P1.4 – Task 4 – Explain the importance of setting SMART objectives to produce possible solutions and how these objectives can have an impact on the success of a project.
P1.5 – Task 5 – Explain the importance of pre-designing Aspects of a system and how a good system plan can have an impact on the success of a project production.
P1.6 – Task 6 – Explain the importance of setting specific Team Roles in terms of Authority, Responsibility and Accountability and how this can have an impact on the success of a project.
P1.7 – Task 7 – Explain the importance of setting specific Scheduling Targets in terms of Event, Activity and Span Time and how this can have an impact on the success of a project.
P1.8 – Task 8 – With the use of specific tables, explain the importance of setting specific Finding Targets and how this can have an impact on the success of a project.
P1.9 – Task 9 – Explain the importance of organising User Documentation and the need for precision and quality in terms of addressing user issues.
P1.10 – Task 10 – Explain the importance of Testing and Maintenance, discuss different methods available and explain with examples how these can have an impact on the success of a project.

## Slide 46: Assessment Task List – Part 2
P1.11 – Task 11 – Explain the importance of Training and Launching and how the quality and timing of these can have an impact on the success of a project.
P1.12 – Task 12 – Explain the importance of Feedback and Project Reviewing and how assessing the failures and successes of a project can have an impact on the success of a future project.
P2.1 – Task 13 – Explain with examples the importance of using Current, Prior and Researched information for project management and how this can have an impact on the success of a project.
P2.2 – Task 14 – Explain the importance of organising Personnel in terms of Work Activity, Considered History and Work Effort and how this can have an impact on the success of a project.
P2.3 – Task 15 – Explain with examples the importance of planning for specific Resources spends in terms of Direct and Indirect costs and how this can have an impact on the success of a project.
P2.4 – Task 16 – Explain with examples the importance of planning for specific Resources spends in terms of Equipment and Software costs and how this can have an impact on the success of a project.
P2.5 – Task 17 – Explain with examples the importance of Project Management Software and how this can have an impact on the success of a project.
P3.1 – Task 18 – Explain the importance of Preparing Risk Analysis information in terms of Risk, Category and Probability and explain how this can have an impact on the success of a project
P3.2 – Task 19 – Explain with examples the importance of management leadership and Communication between client and project manager and how failing on this issue can have an impact on the success of a project.
M2.1 – Task 20 – Using your chosen project, explain the impact Lack of Leadership and Poor Communication would have on a project.

## Slide 47: Assessment Task List – Part 3
P3.3 – Task 21 – Explain with examples how external factors including conflict with the client can have an impact on the success of a project.
M2.2 – Task 22 – Using your chosen project, explain the impact External Factors and Conflicts would have on a project.
P3.4 – Task 23 – Explain with examples how Poor testing and Finished Quality of Product can have an impact on the success of a project.
M2.3 – Task 24 – Using your chosen project, explain the impact Poor testing and Quality of the Finished Product would have on a project.
P3.5 – Task 25 – Explain with examples how Unrealistic Timescales and Poor Progress Tracking can have an impact on the success of a project.
M2.4 – Task 26 – Using your chosen project, explain the impact Unrealistic Timescales and Poor Progress Tracking would have on a project.
P3.6 – Task 27 – Explain with examples how not following Internal Guidelines and being aware of Legislation can have an impact on the success of a project.
M2.4 – Task 28 – Using your chosen project, explain the impact Internal Guidelines and Awareness of Legislation would have on a project.
M1.1 - Task 29 – Produce a report that describes and compares three Project Management Methodologies that are used within Business Planning.
M1.2 – Task 30 – Research and describe the range of advantages and disadvantages of these methodologies