## Slide 1: Unit 09
Project Planning with IT
Y/601/7321
LO2 - Be able to plan projects using IT

## Slide 2: LO2 - Assessment Criteria
Learning Outcome (LO) The learner will: |  | Pass The assessment criteria are the pass requirements for this unit. The learner can: |  | Merit For merit the evidence must show that, in addition to the pass criteria, the learner is able to: | Distinction For distinction the evidence must show that, in addition to the pass and merit criteria, the learner is able to:
1 | Understand how projects are managed | P1 | Illustrate typical phases of a project life cycle |  | 
 |  | P2 | Explain the resources available to support the project manager | M1 Compare different project methodologies | 
 |  | P3 | Discuss issues affecting project management | M2 Explain the impact identified issues would have on a project | 
2 | Be able to plan projects using IT | P4 | Produce a project specification |  | 
 |  | P5 | Plan a defined project using IT | M3 Create a PERT chart for your defined project | D1 Evaluate the use of Gantt and PERT Charts in project planning
3 | Be able to follow project plans | P6 | Follow a project plan to carry out a defined project | M1 Use advanced editing tools to enhance images | 
4 | Be able to review the project management process | P7 | Carry out a review of the project management process |  | D2 Recommend improvements for future projects using the findings from the project review

## Slide 3: Assessment Criteria P4 and P5
Assessment Criterion P4 - The assessment criterion P4 must be evidenced by the learner producing a project specification. The learner is required to include the following in their project specification; identification of clients, stakeholders and target audience, requirement for the project solution, outline the project solution, benefits of the suggested project solution, how success of the project solution will be measured, any constraints which need to be considered, identifying the project deliverables and any ethical, sustainable and health and safety issues. This could be presented as a report.
Assessment Criteria P5 - The assessment criterion P5 must be evidenced by the learner creating a project plan/Gantt chart for a defined project using appropriate IT software. The project plan/ Gantt chart must include activities, deadlines, milestones, dependencies and resources as a minimum. The project plan/Gantt chart could be created in project management software such as Microsoft Project, OpenProj or spreadsheet software. This could be evidence by the submission of the project plan and accompanying documentation.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 4: Assessment Criteria M3 and D1
The merit criterion M3 could be evidenced by the project plan/ Gantt chart information being used to create a PERT chart. The learner must ensure that both the project plan/Gantt chart and PERT chart are detailed to meet the full scope of a multi-task/multi-resource project and contain all required activities and deadlines. The PERT chart should also identify activities which could be run parallel.
For distinction criterion D1 the learner must evaluate the use of Gantt and PERT charts, identifying advantages and disadvantages for both chart types. The learner is also required to review and compare the different software used to create the chart. This could be evidenced by a report with screen captures, charts and narrative.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 5: LO2 - Be able to plan projects using IT
Be able to plan projects using IT
Learners need to be taught the requirements for a project specification and should be provided with details of the kinds of information that should be included in a project specification. They should then explore the details needed for the specification as smaller groups with consideration for end of project reporting – if it isn’t recorded, it can’t be reported. Learners should then develop and complete a brief project specification for a given project, this could be done by learners listing items required for a specification and listing ideas for each of the items either on their own or in pairs/small groups. The brief project details could then be discussed further as a larger group to ensure that all areas were covered in detail and to identify further details required within a specification to ensure accuracy in planning.
Learners should be shown how to use a project planning tool such as Microsoft Project, OpenProj or possibly spreadsheet software to create a Gantt chart. They should be shown how to add resources, deadlines, dependencies and milestones to the Gantt chart and be taught the importance of accuracy of information. Learners could then create a Gantt chart for the given project previously used. They should be shown how to create a PERT chart using relevant software rather than by hand.
Using the Gantt and PERT charts previously created, in pairs learners could discuss the advantages and disadvantages for each of the chart types and software used. They could then give feedback to the group.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 6: P4.2 – Project Specification - Stakeholders
Projects are frequently poorly planned. Project managers usually agree that their companies do not give due care and attention to planning, the process that occurs after initiation. What often happens out of the purview of the project manager is a commitment to do something - develop a product, service, or process. While the high-level planning process may have been completed, this may have resulted in a false sense of confidence that a plan or approach is in place to execute the project. Just a ‘‘few minor details’’ are omitted that should only need a few hours to plan.
For your project you will need to identify all the specific characteristics that would be necessary to hand a project over to someone else and have them off and running with it. There will be a need to identify all the conditions for the project before starting.
P4.1 - Task 1- Using the Project Plan attached, Identify the clients, stakeholders and target audience.

## Slide 7: P4.2 – Project Specification - Requirements
The first level of needs analysis determines the preferences that drive the project requirements. At the end of the day, individuals prefer certain processes, schedules, or activities for the structure of the project. These Requirement define how the particular project will be implemented. If the project is a solution to a problem, this step defines how the solution will be installed. If the project makes use of an opportunity, this step outlines how the opportunity will be addressed, taking into consideration the preferences of those involved in the project.
Requirement needs typically define the parameters of the project in terms of scope, timing, budget, staffing, location, technology, deliverables, and the degree of disruption allowed. Requirement needs are developed from the input of several stakeholders rather than from one individual. For example, participants in the project (those who must make it work) may have a particular Requirement, but the Requirement could exhaust resources, time, and budgets. The immediate manager’s input may help minimise the amount of disruption and maximise resources. The funds that can be allocated are also a constraining resource.
P4.2 - Task 2 - Using the Project Plan attached, identify any requirements necessary for the project solution.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 8: P4.3 – Project Specification – Project Scope
One of the most important and most difficult aspects of project management is defining the scope of a project. Scope refers to all the work involved in creating the products of the project and the processes used to create them. Deliverables can be product related, such as a piece of hardware or software, or process-related, such as a planning document or meeting minutes. Project stakeholders must agree what the products of the project are and, to some extent, how they should be produced to define all of the deliverables
The project scope statement is prepared to describe the nature and extent of the work effort that will be performed to achieve project objectives. The scope statement is a broader characterisation of how the project objectives will be achieved.
Essentially, the scope statement indicates what is to be accomplished, when and where it will be accomplished, by which individuals or groups, and at what cost, schedule, and resource utilisation thresholds. It can also be a statement of what will not be achieved as in the scope statement places boundaries on the work effort. The challenge for the scope statement developer is to neither understate the scope in a way that does not sufficiently guide the project nor overstate the scope so as to inundate project team users with unnecessary detail and complexities that are better placed elsewhere, perhaps in accompanying project plans.
P4.3 - Task 3 - Using the Project Plan attached, outline the project scope for your project.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 9: P4.4 – Project Specification – Project Benefits
Specifying before the project starts what the benefits of the completed project will be can give the project manager a guide to the value of each phase, keeping in mind the end goal. Each project is different and each has a core benefit the client hopes the project will achieve. Benefits come in different forms:
Financial Benefits - cost versus - such measures as revenue returned and cash flow impacts resulting from the project effort, expense reduction (or increase) resulting from the project management approach, and further business opportunities resulting from project success (or failure)
Technical Benefits - cost versus such measures as opportunity for the introduction of new products and the potential for technical innovation or breakthrough
Core Competency Enhancement - cost versus such measures as demonstration of new or enlarged performance capability, expansion of project manager and project team member skill and experience
Harmony with Corporate Culture - cost versus such measures as achievement of business objectives that endorse or enhance business functions, traditions and values.
P4.4 - Task 4 - Using the Project Plan attached, outline the potential short and long term benefits of the completed project on business functions.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 10: P4.5 – Project Specification – Success criterion
At the initiation stage of any project, this is where the project manager will get the best chance define success. At the very outset they can agree on the project’s success criteria - key elements that need to be delivered for the project to be successful. These criteria will then help guide the project manager throughout the project. Of course, if it’s obvious from their initial discussions that the success criteria aren’t clearly linked to the business purpose of the project, again, they’ve uncovered a potential stumbling block very early, before too much energy has been invested in the project.
These success criteria describe what you’re trying to achieve in the project itself, as well as the long-term business benefits that are expected as the pay back for the initial investment in the project. One of the reasons that keeping the Project initiation Document up to date as the project progresses, and changes are made to its scope, time, quality, and cost factors, is to make sure that these success criteria are still relevant.
P4.5 - Task 5 - Using the Project Plan attached, outline the success criterion for your project.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 11: P4.6 – Project Specification - Constraints
Not all project constraints are equal. The prioritisation of constraints is performed on a project-by-project basis. The Client’s’ involvement in this decision is essential. Secondary factors are also considered to be constraints and may be more important than the primary constraints.
For example, years ago, at Disneyland and Disney World, the project managers designing and building the attractions had six constraints:
  ◾ Time ◾ Cost ◾ Scope ◾ Safety ◾ Aesthetic value ◾ Quality
At Disney, the last three constraints, those of safety, aesthetic value, and quality, were considered locked in constraints that could not be altered during trade-offs. All trade-offs were made on time, cost, and scope.
The importance of the components of success can change over the life of the project. For example, in the initiation phase of a project, scope may be the critical factor for success, and all trade-offs are made on the basis of time and cost. During the execution phase of the project, time and cost may become more important, and then trade-offs will be made on the basis of scope.
P4.6 - Task 6 - Using the Project Plan attached, outline the project constraints that may have an impact on the finished product.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 12: P4.6 – Project Specification - Deliverables
Project deliverables are those products and services presented to the customer as a result of project work accomplished, and, to a large extent, they represent the achievement of specified project objectives.
For project definition purposes, project deliverables are described at a high level and represent only those items that will be transferred to the customer. Therefore, internal or interim deliverables are not usually a part of the project definition, but they may be specified in accompanying plans when they are developed.
Project deliverables are normally aligned with the completion of certain project activities, as may be specified in the Work Breakdown Structure, which is normally constructed during project planning but only an overview of the deliverables can be identified at the early stage. The project manager can then specify anticipated project deliverables within project phases. This list of project deliverables will need to be reviewed and refined as more detailed requirements and information from the customer are applied to the project planning effort.
Examples of deliverables that can be guaranteed include the finished product, documentation, training and support needs.
P4.6 - Task 6 - Using the Project Plan attached, outline the project deliverables and match these against the success criteria set in the previous task.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 13: P4.7 – Project Specification – Assumptions and Constraints
Project definition provides an early description of what has to be accomplished in order to have a successful project outcome. Many of the project activities, events, and conditions that are initially considered are based on items such as “status quo,” “common knowledge,” “routine responses,” and “reasonable expectations.” These may be “common and reasonable,” but since they are not necessarily factual, there could be alternate perspectives, and they need to be stated as the project’s assumptions and constraints.
Project Assumptions are factors considered to be true, real, or certain for the purposes of making project decisions. Assumptions involve a degree of risk. Examples of assumptions to be considered include specifications or statements related to:
  Budget and resource availability
  Time requirements
  Staff availability, training requirements, and experience
  Number and identity of stakeholders
  Level of project complexity
  Size and duration of the project
  External needs
  Extent of risks
  Level of technical capabilities
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 14: P4.7 – Project Specification – Assumptions and Constraints
Project Constraints are generally known factors that will limit project management options. Specifically, constraints may restrict the planning of project cost, schedule, and resources needed to achieve the project scope; affect when or how an activity can be scheduled; or lead to team pressure to complete the project on time, within budget, and according to specification. Examples of constraints to be considered include
Cost and Scheduling
Staffing requirements or availability
Available technology
Funding availability, Contractual factors and Government regulations
Risk factors
Scope expectations and feasibility
Market or economic factors
Organizational structure and Culture
Similarly, constraints in and of themselves are not project risks. However, they could become risks if the constraining condition unexpectedly changes to affect project performance. Constraints should be monitored and validated on an
On-going basis.
P4.7 - Task 7 - Using the Project Plan attached, outline the project assumptions and constraints that can have an impact on the success of a project.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 15: P4.8 – Project Specification – Potential Issues
All forms of issues can come up when it comes to project management, some can be foreseen, others are a surprise, not everything can be guaranteed.
Ethical Issues - Project managers will be working with different stakeholders that have a direct or indirect interest in the outcome of their project. They may deal with executives or managers from their bsuiness or even those outside of it. They may deal with vendors or suppliers as well as people spanning a wide spectrum, from security to marketing to information systems and finance. This unique set of circumstances can cause ethical dilemmas to occur quickly easily. For example, some executives may be more powerful than the customer and, thereby, pressure the team or the project manager to put the customer’s interests aside even though the customer is paying for the project. Unique circumstances may encourage team members to get too close with suppliers, thereby weakening or destroying objectivity and independence as well as reining the charge of conflict of interest when agreements are made with one vendor or another.
And there is the morality of hiring and cost cutting, who is the best for the job may not be who is right for the job, similarly if a job is over budget or over time what do you cut, safety or data protection.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 16: P4.8 – Project Specification – Potential Issues
Sustainable – Our definition of project success for decades was meeting 3 constraints. Time and cost were two of the three sides to the triangle, and the third side was either scope, technology, performance or quality, depending on who was defining success. Whenever other constraints appeared, such as risk, business value, image reputation, safety and sustainability, they were inserted into the centre of the triangle with the belief that they either elongated or compressed the boundary triple constraints.
Sustainability is now more common an issue with in-built redundancy, being green and waste. But sustainability comes at a cost, did Apple or Samsung think of this when it hired Foxconn, do white good manufacturers factor this in. But it is an issue with governments, specifically when it comes to guaranteeing funding.
Health and Safety – In the same vein as Sustainability, factoring in this when it comes to costing can be an issue when money is running out or a project over budget or off schedule. There are steps that can be taken but are they enough for your project, adding protection but not being secure, adding safety measures but not enough. For instance testing new cars with crash test dummies is too expensive over 30mph but necessary under 30mph. Tests are done, the box ticked, should we move on or force the expense because it is necessary.
P4.8 - Task 8 - Using the Project Plan attached, outline the potential project issues (e.g. ethical, sustainable, health and safety).
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 17: P5 – Project Planning - Planning Production
Project plan - Now the project has been planned and the scope agreed, it is time to start planning the project. Using the Project Plan template created for P4 you will need to plan your project including activities, deadlines, milestones, dependencies and resources as a minimum. This can either be done in Excel, Microsoft Project template or in OpenProj.
P5.1 – Task 9 - Using this Project Plan, complete a Project Workflow Gantt Chart that describes the Timings and Milestones of your selected project. Use the template Unit 09 - LO2 - P5 - Schedule and Timescale as a guide.
P5.2 – Task 10 - Using this Project Plan and Gantt Chart, complete a Project and Budgeting Spreadsheet that describes the risk analysis and costing breakdown of the selected project. Use the template Unit 09 - LO2 - P5 - Project Breakdown as a guide.
P5.3 – Task 11 – Prepare this collected information above into a usable format within the Project Plan in the form of a report.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 18: M3.1 - Be able to plan projects using IT
To make it easier for project managers to demonstrate the information gathered from the project plan and project files, they will need to create a series of flow charts for the client. With Microsoft project and OpenProj this is an easy task to convert information from a Gantt Chart into a Pert.
With Excel this is not so straight forward but can be managed the rough manual creation of elements and flow arrows.
You must ensure that both the project plan/Gantt chart and PERT chart are detailed to meet the full scope of a multi-task/multi-resource project and contain all required activities and deadlines. The PERT chart should also identify activities which could be run parallel.
M3.1 - Task 12 – Using the information from the Gantt chart, produce a pert chart that defines the chain of Timings, Deadlines and Milestones activities for your Project.
M3.2 – Task 13 – Using section 12 of your Project Plan, state the Milestones and parallel Processes of your Project Schedule.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 19: D1.1 - Be able to plan projects using IT
With the Project plans complete and the analysis and drafting charts in place you will need to decide how to present this information to your client. Overkill is possible so you will need to analyse which graphic method best explains the project plan to them.
D1.1 – Task 14 - Evaluate the use of Gantt and PERT charts, identifying advantages and disadvantages for both chart types.
Similarly the client will need to know which software will be best to stick with for the duration of the project. This should be based on:
  Easy of Use/Simplicity of Layout
  Graphical results
  Ability to highlight Milestones and Deadlines
  Cross compatibility
  Learning curve
D1.2 – Task 15 - Compare with evidence the different software used to create the Project charts using the selected criteria.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 20: Task List
P4.1 - Task 1- Using the Project Plan attached, Identify the clients, stakeholders and target audience.
P4.2 - Task 2 - Using the Project Plan attached, identify any requirements necessary for the project solution.
P4.3 - Task 3 - Using the Project Plan attached, outline the project scope for your project.
P4.4 - Task 4 - Using the Project Plan attached, outline the potential short and long term benefits of the completed project on business functions.
P4.5 - Task 5 - Using the Project Plan attached, outline the success criterion for your project.
P4.6 - Task 6 - Using the Project Plan attached, outline the project constraints that may have an impact on the finished product.
P4.6 - Task 6 - Using the Project Plan attached, outline the project deliverables and match these against the success criteria set in the previous task.
P4.7 - Task 7 - Using the Project Plan attached, outline the project assumptions and constraints that can have an impact on the success of a project.
P4.8 - Task 8 - Using the Project Plan attached, outline the potential project issues
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8

## Slide 21: Task List
P5.1 – Task 9 - Using this Project Plan, complete a Project Workflow Gantt Chart that describes the Timings and Milestones of your selected project.
P5.2 – Task 10 - Using this Project Plan and Gantt Chart, complete a Project and Budgeting Spreadsheet that describes the risk analysis and costing breakdown of the selected project.
P5.3 – Task 11 – Prepare this collected information above into a usable format within the Project Plan in the form of a report.
M3.1 - Task 12 – Using the information from the Gantt chart, produce a pert chart that defines the chain of Timings, Deadlines and Milestones activities for your Project.
M3.2 – Task 13 – Using section 12 of your Project Plan, state the Milestones and parallel Processes of your Project Schedule.
D1.1 – Task 14 - Evaluate the use of Gantt and PERT charts, identifying advantages and disadvantages for both chart types.
D1.2 – Task 15 - Compare with evidence the different software used to create the Project charts using the selected criteria.
Scenario
Criteria
Tasks
Assessment
1
2
3
4
5
6
7
8